## Dashboard
⬡ ZeroTrust.sh · Internship Executive Dashboard
Intern: Ton Minh Hoang · VNG ZingPlay Studio · Program: 2026-06-09 → 2026-08-01 · Mentor: (Software Manager) Nguyễn Trung Hưng
▐ KEY PERFORMANCE INDICATORS |  |  |  |  | ▐ INTERNSHIP TIMELINE
📋 Total Tasks | ✅ Complete | 🔄 In Progress | ⏰ Days Left | 📈 % Complete | Goal | Jun W3 Jun 16–22 | Jun W4 Jun 23–29 | Jul W1 Jun 30–Jul 6 | Jul W2 Jul 7–13 | Jul W3 Jul 14–20 | Jul W4 Jul 21–27 | Aug W1 Jul 28–Aug 6
G1 — Foundation
G2 — Path A
146 | 0 | 3 | 57 | 0% | G3 — Path B
G4 — Integration
Research (all goals)
▐ PROGRESS BY GOAL
Milestone | Not Started | In Progress | Complete | Blocked
Foundation & Detection Scaffold | 28 | 2 | 0 | 0
Path A: CPG + Taint + LLM Verifier | 32 | 0 | 0 | 0
Path B: Semantic Cost Funnel | 33 | 0 | 0 | 0
Integration, Report & Demo | 21 | 0 | 0 | 0
Scientific Research | 29 | 1 | 0 | 0
TOTAL | 143 | 3 | 0 | 0

## G1 - Foundation
ZeroTrust.sh · G1 — Foundation & Detection Scaffold
Intern: Ton Minh Hoang · VNG ZingPlay Studio · Goal: Rule suite + Go CLI + Ingestion layer + Finding schema · Deadline: 2026-06-27
ID | Name | Type | Start Date | End Date | PERT O (h) | PERT ML (h) | PERT P (h) | PERT E (h) | Actual Hrs | Status | Owner | Notes
1.M1 | Semgrep + ast-grep Rule Suite | MILESTONE | 2026-06-11 | 2026-06-16 | 14 | 20 | 30 | 20.7 |  | In Progress |  | Python rules in progress (per CLAUDE.md); Java rules not yet started
1.M1.T1 | Build synthetic vulnerable test codebase (Python + Java) | TASK | [5 empty] | 3 |  | In Progress | Hoang | Must exist before rules can be validated; trigger every rule class
1.M1.T2 | Semgrep rules — LLM prompt injection patterns | TASK | [5 empty] | 2 |  | In Progress | Hoang | Python rules in progress; cover direct + indirect injection
1.M1.T3 | Semgrep rules — security-control bypass comments | TASK | [5 empty] | 1.5 |  | Not Started | Hoang | e.g. # nosec, // nolint, AI-inserted disable comments
1.M1.T4 | Semgrep rules — hardcoded AI API keys | TASK | [5 empty] | 1.5 |  | Not Started | Hoang | OpenAI, Anthropic, Cohere, HuggingFace key patterns
1.M1.T5 | Semgrep rules — MCP server config injection (.mcp.json) | TASK | [5 empty] | 2 |  | Not Started | Hoang | Novel surface; no community rules exist; highest-priority unique claim
1.M1.T6 | Semgrep rules — agent instruction file injection (.cursor/rules, AGENTS.md, CLAUDE.md, GEMINI.md, copilot-instructions.md) | TASK | [5 empty] | 2.5 |  | Not Started | Hoang | First tool to cover this vector; key demo talking point
1.M1.T7 | ast-grep structural matching rules (languages with weak Semgrep community packs) | TASK | [5 empty] | 3 |  | Not Started | Hoang | YAML rule format; target Rust, Kotlin, C# gaps in Semgrep OSS packs
1.M1.T8 | Rule validation + false-positive audit against test codebase | TASK | [5 empty] | 3 |  | Not Started | Hoang | Each rule must fire on >= 1 test case; zero FPs on a clean-code control
1.M1.T9 | CI-runnable test harness | TASK | [5 empty] | 2.2 |  | Not Started | Hoang | Makefile or shell script; pass/fail output per rule class; runs in < 60s
1.M2 | Go CLI Core | MILESTONE | 2026-06-16 | 2026-06-20 | 12 | 18 | 26 | 18.3 |  | Not Started |  | Claude Code compresses ML est. ~35%; single binary from day one
1.M2.T1 | Go module init + project directory structure | TASK | [5 empty] | 1 |  | Not Started | Hoang | Go 1.22+; cmd/, internal/, pkg/ layout; add .gitignore
1.M2.T2 | CLI argument parsing + TOML config schema | TASK | [5 empty] | 3 |  | Not Started | Hoang | cobra + viper (or stdlib flag); config fields: model-path, output-dir, scan-target, log-level
1.M2.T3 | Directory walk + file-type detection (language routing table) | TASK | [5 empty] | 3 |  | Not Started | Hoang | filepath.WalkDir; extension -> language enum map; respect .gitignore
1.M2.T4 | ZIP archive extract + ingestion path | TASK | [5 empty] | 2 |  | Not Started | Hoang | archive/zip; extract to OS temp dir; cleanup on exit (defer)
1.M2.T5 | Pluggable Finding channel interface definition | TASK | [5 empty] | 3.5 |  | Not Started | Hoang | chan Finding or writer interface; all pipeline components write here; schema frozen after M1.4
1.M2.T6 | Cross-compile build pipeline (darwin/linux/windows, amd64/arm64) | TASK | [5 empty] | 2 |  | Not Started | Hoang | Makefile targets; GoReleaser optional; verify binary size < 20 MB
1.M2.T7 | Smoke test on real directory + binary install verification | TASK | [5 empty] | 3.8 |  | Not Started | Hoang | Binary accepts path arg, scans synthetic codebase, exits 0; test on macOS + Linux
1.M3 | Ingestion Layer — Model Integrity Verifier + Differential Indexer | MILESTONE | 2026-06-20 | 2026-06-25 | 12 | 18 | 28 | 18.7 |  | Not Started |  | MIV is a unique security property vs all competitors; demo talking point
1.M3.T1 | Model Integrity Verifier: SHA256 hash function for GGUF file | TASK | [5 empty] | 1 |  | Not Started | Hoang | crypto/sha256; stream file in chunks to avoid OOM on large (4-8 GB) models
1.M3.T2 | Model Integrity Verifier: pinned manifest format + loader | TASK | [5 empty] | 2 |  | Not Started | Hoang | JSON manifest: model name, version, expected SHA256; bundled in binary via go:embed
1.M3.T3 | Model Integrity Verifier: startup check — block scan + user-facing error on mismatch | TASK | [5 empty] | 2 |  | Not Started | Hoang | Exit code 1 + clear error message; never silently continue on mismatch
1.M3.T4 | Differential Indexer: per-file hash computation | TASK | [5 empty] | 2 |  | Not Started | Hoang | xxHash (faster) or SHA256 per file; parallel via goroutines over file list
1.M3.T5 | Differential Indexer: hash cache store | TASK | [5 empty] | 2.5 |  | Not Started | Hoang | BoltDB at ~/.zerotrust/cache/<project-hash>.db; JSON flat-file as fallback
1.M3.T6 | Differential Indexer: dirty-file computation (current vs cached hash diff) | TASK | [5 empty] | 2 |  | Not Started | Hoang | Returns []FileEntry of changed + new files only; passes to pipeline entry point
1.M3.T7 | Differential Indexer: cache update on successful scan completion | TASK | [5 empty] | 1.5 |  | Not Started | Hoang | Only write on clean exit (code 0); never persist partial scan state
1.M3.T8 | Integration test: tampered GGUF file -> scan blocked | TASK | [5 empty] | 2.5 |  | Not Started | Hoang | Flip one byte in model file; assert exit code 1 + correct error message
1.M3.T9 | Integration test: repeat scan -> only changed files re-scanned | TASK | [5 empty] | 3.2 |  | Not Started | Hoang | Full scan, modify 1 file, rescan; assert only modified file enters pipeline
1.M4 | Canonical Finding Schema + CLI Output | MILESTONE | 2026-06-25 | 2026-06-27 | 6 | 10 | 16 | 10.3 |  | Not Started |  | Schema locked after this milestone — no breaking changes in G2/G3/G4
1.M4.T1 | Finding struct definition in Go | TASK | [5 empty] | 2 |  | Not Started | Hoang | Fields: CWE, Severity, File, LineStart, LineEnd, Source, Confidence, Evidence, TaintPath (omitempty)
1.M4.T2 | Severity tier constants (BLOCK / HIGH / MEDIUM / LOW / SUPPRESSED) | TASK | [5 empty] | 0.5 |  | Not Started | Hoang | Typed string constants — not bare strings; use in all components
1.M4.T3 | JSON serialization for Finding struct | TASK | [5 empty] | 2 |  | Not Started | Hoang | encoding/json; omitempty on optional fields; test marshal/unmarshal roundtrip
1.M4.T4 | Human-readable stdout formatter (colorized, grouped by severity) | TASK | [5 empty] | 3 |  | Not Started | Hoang | BLOCK=red, HIGH=orange, MEDIUM=yellow, LOW=blue; respect NO_COLOR env var
1.M4.T5 | Unit tests: struct construction, JSON serialization, stdout output | TASK | [5 empty] | 2.8 |  | Not Started | Hoang | Table-driven tests; golden file for stdout formatter output
1.BUF | G1 Buffer | BUFFER | 2026-06-11 | 2026-06-27 |  |  |  | 10 |  |  |  | Absorbs: Joern env surprises (R-01), tool version mismatches, sick days; cut stretch items before touching buffer

## G2 - Path A
ZeroTrust.sh · G2 — Path A: CPG + Taint + LLM Verifier
Intern: Ton Minh Hoang · VNG ZingPlay Studio · Goal: Joern CPG + taint queries + Python worker IPC + LLM Verifier · Deadline: 2026-07-18
ID | Name | Type | Start Date | End Date | PERT O (h) | PERT ML (h) | PERT P (h) | PERT E (h) | Actual Hrs | Status | Owner | Notes
2.M1 | Joern CPG Build Pipeline | MILESTONE | 2026-06-30 | 2026-07-07 | 16 | 25 | 40 | 26 |  | Not Started |  | Highest-risk milestone in plan; Joern env setup is the most common blocker; plan for 1-2 debug days
2.M1.T1 | Joern installation + JVM setup + version-pin | TASK | [5 empty] | 2 |  | Not Started | Hoang | Pin exact Joern version in config (e.g. v4.x); Java 11+; confirm `joern --version` exits 0
2.M1.T2 | Joern server startup verification | TASK | [5 empty] | 2.5 |  | Not Started | Hoang | Start Joern in server mode; send a no-op query; confirm response; measure cold-start time
2.M1.T3 | Go subprocess wrapper: spawn Joern process via os/exec | TASK | [5 empty] | 4 |  | Not Started | Hoang | exec.Command; capture stdout/stderr; handle premature exit; log all Joern stderr to debug file
2.M1.T4 | Go subprocess wrapper: health check + retry logic | TASK | [5 empty] | 2.5 |  | Not Started | Hoang | Poll Joern REST endpoint or REPL; max 3 retries; fail scan with clear error if Joern unresponsive
2.M1.T5 | CPG generation: invoke Joern on source directory, capture output | TASK | [5 empty] | 4.5 |  | Not Started | Hoang | Feed only dirty files from Differential Indexer; enforce <= 5K LOC gate before invoking; measure build time
2.M1.T6 | CPG serialization format decision + implementation | TASK | [5 empty] | 4 |  | Not Started | Hoang | Decision: in-memory graph vs file-based export; chosen format must be readable by both Path A and Path B without re-parse
2.M1.T7 | Shared CPG access interface (Path A + Path B) | TASK | [5 empty] | 3.5 |  | Not Started | Hoang | Go interface with at least: QueryNodes(type), QueryEdges(src, dst), GetCallGraph(); G3 components read from this interface
2.M1.T8 | Codebase size gate (<= 5K LOC) + query timeout handling | TASK | [5 empty] | 2 |  | Not Started | Hoang | Count LOC before CPG build; reject with user-facing error if over limit; kill Joern process on timeout (default 60s)
2.M1.T9 | Integration test: CPG built successfully on synthetic test codebase | TASK | [5 empty] | 1.3 |  | Not Started | Hoang | Assert CPG non-empty; assert node types present (Method, Call, Identifier); assert build time < 30s
2.M2 | Taint Analysis Query Layer | MILESTONE | 2026-07-07 | 2026-07-11 | 14 | 22 | 34 | 22.7 |  | Not Started |  | Taint paths produced here are the evidence fed into M2.3 LLM Verifier prompt
2.M2.T1 | Source / sanitizer / sink taxonomy definition per language | TASK | [5 empty] | 3 |  | Not Started | Hoang | Languages: Java, Python, JS/TS, Go; document each category in a YAML taxonomy file
2.M2.T2 | Joern traversal queries: external-input source nodes | TASK | [5 empty] | 3.5 |  | Not Started | Hoang | Scala DSL; sources: HTTP params, env vars, file reads, stdin, deserialized objects
2.M2.T3 | Joern traversal queries: sanitizer nodes | TASK | [5 empty] | 3.5 |  | Not Started | Hoang | Sanitizers: input validation, HTML encoding, parameterized queries, allowlist checks
2.M2.T4 | Joern traversal queries: dangerous sink nodes | TASK | [5 empty] | 3.5 |  | Not Started | Hoang | Sinks: eval, exec/system, SQL string concat, deserialize, file write to user-controlled path, SSRF URL construction
2.M2.T5 | Taint flow -> Finding struct mapping + CWE assignment | TASK | [5 empty] | 3.5 |  | Not Started | Hoang | Each taint flow serialized: source node, sanitizer gaps, sink node, traversal path; CWE assigned by sink type
2.M2.T6 | Multi-language taint query test suite | TASK | [5 empty] | 3 |  | Not Started | Hoang | One taint case per language (Java, Python, JS/TS, Go); each must be detected; add to CI harness
2.M2.T7 | False positive baseline measurement on synthetic clean code | TASK | [5 empty] | 2.7 |  | Not Started | Hoang | Run taint queries on clean-code control set; count FPs; record as baseline before LLM Verifier applied
2.M3 | Python Worker Bootstrap + LLM Verifier (False Positive Filter) | MILESTONE | 2026-07-11 | 2026-07-16 | 18 | 29 | 42 | 29.3 |  | Not Started |  | Two parts: (1) IPC boundary — built once, reused by all G3 ML components; (2) LLM Verifier using XGrammar
2.M3.T1 | Python venv setup + requirements.txt | TASK | [5 empty] | 1.5 |  | Not Started | Hoang | Packages: xgrammar, ollama (Python client), httpx; pin versions; venv at worker/venv/
2.M3.T2 | Python worker main.py: message dispatcher | TASK | [5 empty] | 3 |  | Not Started | Hoang | Reads NDJSON from stdin in a loop; dispatches by `type` field (llm_verify, classify, summarize, llm_scan, ping, shutdown)
2.M3.T3 | Go worker-manager: spawn Python worker via os/exec + pipe setup | TASK | [5 empty] | 3.5 |  | Not Started | Hoang | exec.Command('python3', '-u', 'worker/main.py'); -u disables output buffering; pipe stdin + stdout; route stderr to log
2.M3.T4 | Go worker-manager: health-check ping + restart-on-crash logic | TASK | [5 empty] | 2.5 |  | Not Started | Hoang | Send ping; await pong; detect closed stdout pipe; attempt 1 restart; fallback to direct Ollama HTTP on second failure
2.M3.T5 | NDJSON protocol: request/response schema + Go client library | TASK | [5 empty] | 3 |  | Not Started | Hoang | Request: {id, type, payload}; Response: {id, status, result} or {id, status, error}; thread-safe
2.M3.T6 | Python worker: Ollama HTTP client integration | TASK | [5 empty] | 2.5 |  | Not Started | Hoang | Call Ollama REST API (/api/generate); pass model name from config; handle timeout; verify model loaded
2.M3.T7 | Python worker: XGrammar JSON schema enforcement on LLM output | TASK | [5 empty] | 3 |  | Not Started | Hoang | Verdict JSON schema: {verified: bool, confidence: float, rationale: str}; XGrammar enforces at generation time
2.M3.T8 | Taint-flow prompt template | TASK | [5 empty] | 3.5 |  | Not Started | Hoang | Template inputs: taint flow path, sink type, reachability condition, sanitizer gaps; test with 5+ real taint flows
2.M3.T9 | Verdict routing back to Go Finding channel | TASK | [5 empty] | 2 |  | Not Started | Hoang | verified=true -> write Finding to channel; verified=false -> discard; confidence score written to Finding.Confidence
2.M3.T10 | Latency benchmark: per-finding round-trip time | TASK | [5 empty] | 2 |  | Not Started | Hoang | Target: < 2s per finding (Go send -> Python -> Ollama -> XGrammar -> Go receive); log p50/p95
2.M3.T11 | Accuracy test: TP/FP rate on synthetic taint findings | TASK | [5 empty] | 2.8 |  | Not Started | Hoang | Run LLM Verifier on taint findings from M2.2; target >= 88% FP reduction; record as A-18 pre-check
2.M4 | Path A Integration Test Suite | MILESTONE | 2026-07-16 | 2026-07-18 | 6 | 10 | 16 | 10.3 |  | Not Started |  | Natural pause point before G3; Joern CPG confirmed as shared infra; mentor review can be scheduled here
2.M4.T1 | Synthetic test case set: 10+ vulnerable functions (one per CWE class) | TASK | [5 empty] | 3 |  | Not Started | Hoang | CWE classes: CWE-89 SQL injection, CWE-78 OS command injection, CWE-22 path traversal, CWE-502 deserialization, CWE-611 XXE, CWE-918 SSRF, CWE-79 XSS, CWE-327 weak crypto, CWE-798 hardcoded creds, CWE-94 code injection
2.M4.T2 | End-to-end pipeline run (ingestion -> Joern -> taint -> LLM Verifier -> Finding output) | TASK | [5 empty] | 2 |  | Not Started | Hoang | Single `zerotrust scan ./test-codebase` command; all 10+ CWE cases must produce Findings
2.M4.T3 | Precision/recall baseline measurement | TASK | [5 empty] | 2 |  | Not Started | Hoang | Record in docs/benchmarks/g2_baseline.md; this is the baseline G3 Path B will improve on
2.M4.T4 | Integration break fixes | TASK | [5 empty] | 2 |  | Not Started | Hoang | Resolve any failures found in T2/T3; if a fix takes > 4h, escalate as At Risk and consume buffer
2.M4.T5 | Performance profiling: full scan time on 5K LOC synthetic codebase | TASK | [5 empty] | 1.3 |  | Not Started | Hoang | Measure: CPG build time, taint query time, LLM Verifier time, total wall clock; target total < 5 min on 5K LOC
2.BUF | G2 Buffer | BUFFER | 2026-06-30 | 2026-07-18 |  |  |  | 13 |  |  |  | Primary risk: R-01 Joern env setup surprises (OOM, Scala DSL learning curve); secondary: mentor review cycle

## G3 - Path B
ZeroTrust.sh · G3 — Path B: Three-Tier Semantic Cost Funnel
Intern: Ton Minh Hoang · VNG ZingPlay Studio · Goal: Heuristic Targeting + UniXcoder + Semantic Summarizer + LLM ReAct · Deadline: 2026-08-01
ID | Name | Type | Start Date | End Date | PERT O (h) | PERT ML (h) | PERT P (h) | PERT E (h) | Actual Hrs | Status | Owner | Notes
3.M1 | Heuristic Targeting + Call Graph + CVE Enrichment | MILESTONE | 2026-07-21 | 2026-07-25 | 12 | 18 | 28 | 18.7 |  | Not Started |  | Reads Joern CPG from G2 (no re-parse); Trivy replaced by OSV-Scanner (CVE-2026-33634 supply chain compromise)
3.M1.T1 | CPG node-type queries — external-input nodes | TASK | [5 empty] | 2.5 |  | Not Started | Hoang | Query CPG for HTTP params, env vars, file reads, stdin, deserialized objects; language-agnostic via shared CPG schema
3.M1.T2 | CPG node-type queries — auth-boundary nodes | TASK | [5 empty] | 2 |  | Not Started | Hoang | Identify authentication/authorization check points; missing guard detection starts here
3.M1.T3 | CPG node-type queries — AI agent config file nodes | TASK | [5 empty] | 2 |  | Not Started | Hoang | MCP configs, .cursor/rules, AGENTS.md, CLAUDE.md, GEMINI.md; unique detection surface
3.M1.T4 | Call graph extraction from Joern CPG | TASK | [5 empty] | 3 |  | Not Started | Hoang | No separate build step — call graph comes from CPG built in G2; extract caller/callee edges; output: Go CallGraph struct
3.M1.T5 | OSV-Scanner Go library integration (github.com/google/osv-scanner/v2) | TASK | [5 empty] | 3 |  | Not Started | Hoang | Direct Go import — no subprocess; scan dependency manifests (go.mod, requirements.txt, pom.xml, package.json)
3.M1.T6 | CVE exact-match auto-flag + routing to findings | TASK | [5 empty] | 2 |  | Not Started | Hoang | If OSV-Scanner returns exact CVE match -> write Finding directly with severity from CVSS; skip further analysis
3.M1.T7 | BOLAZ zero-trust resource ID dataflow flagging | TASK | [5 empty] | 2.5 |  | Not Started | Hoang | Flag all external IDs as untrustworthy until explicit authorization confirmed at each function boundary; targets IDOR/BOLA
3.M1.T8 | Surface list output format for downstream classifier | TASK | [5 empty] | 1.7 |  | Not Started | Hoang | Struct: Surface{ID, File, FunctionName, NodeType, CallGraphDepth, CVEMatches}; passed to M3.2 classifier
3.M2 | UniXcoder Classifier Gate | MILESTONE | 2026-07-25 | 2026-07-28 | 12 | 18 | 28 | 18.7 |  | Not Started |  | Primary LLM cost gate; A-18 calibration point — measure real precision/recall on AI-generated code; window spans weekend
3.M2.T1 | UniXcoder model load in Python worker (extend dispatcher) | TASK | [5 empty] | 2.5 |  | Not Started | Hoang | Add `classify` type handler to Python worker from G2; load UniXcoder-Base-Nine via transformers; pin model version
3.M2.T2 | Go IPC: classify request/response type handling | TASK | [5 empty] | 2 |  | Not Started | Hoang | Send Surface struct as payload; receive {verdict: vulnerable/safe/uncertain, confidence: float}; reuse NDJSON protocol
3.M2.T3 | Confidence threshold calibration (3-band classification) | TASK | [5 empty] | 3 |  | Not Started | Hoang | Tune thresholds: high-conf-safe (dismiss), high-conf-vulnerable (flag direct), uncertain (-> LLM); target uncertain band = 15-25%
3.M2.T4 | High-confidence-safe dismissal routing | TASK | [5 empty] | 1.5 |  | Not Started | Hoang | Surfaces below safe threshold -> dropped silently; log count for cost funnel stats used in demo
3.M2.T5 | High-confidence-vulnerable direct Finding flag routing | TASK | [5 empty] | 1.5 |  | Not Started | Hoang | Surfaces above vulnerable threshold -> write Finding directly to channel; no LLM call; Source field = 'UniXcoder'
3.M2.T6 | Unsupported-language bypass (Rust, Kotlin, Swift, C# -> direct LLM) | TASK | [5 empty] | 1.5 |  | Not Started | Hoang | UniXcoder trained only on Python/Java/JS/TS/Go/Ruby/PHP; unsupported languages skip classifier
3.M2.T7 | A-18 gap measurement: precision/recall on AI-generated code vs BigVul baseline | TASK | [5 empty] | 3.2 |  | Not Started | Hoang | Run classifier on test codebase (AI-generated code); record F1, precision, recall; compare to claimed F1=94.73% on BigVul
3.M2.T8 | Classifier gate integration test: verify < 25% of surfaces reach LLM tier | TASK | [5 empty] | 3.5 |  | Not Started | Hoang | Run full surface set through gate; assert uncertain band <= 25%; if over, re-tune thresholds; log final funnel stats
3.M3 | Call Chain Context Assembler + Semantic Function Summarizer | MILESTONE | 2026-07-28 | 2026-07-31 | 12 | 18 | 28 | 18.7 |  | Not Started |  | LLM never receives raw code — only semantic summaries; aligns with IRIS ICLR 2025 design
3.M3.T1 | Call chain traversal to depth 3 from Joern CPG (caller -> surface -> callee) | TASK | [5 empty] | 4 |  | Not Started | Hoang | Use call graph from 3.M1.T4; traverse depth 3 max; return ordered list [caller, surface, callee]; handle recursive/missing nodes
3.M3.T2 | Multi-function context assembly (structured call chain representation) | TASK | [5 empty] | 3 |  | Not Started | Hoang | Struct: CallChainContext{functions: []FunctionContext, entryPoint, depth}; FunctionContext: name, params, local vars, calls, return type
3.M3.T3 | Semantic summary schema — taint-flow vulnerability class | TASK | [5 empty] | 2 |  | Not Started | Hoang | Fields: untrustedDataSource, sanitizersPresent[], sanitizerGaps[], sinkReached, sinkType
3.M3.T4 | Semantic summary schema — auth-guard vulnerability class | TASK | [5 empty] | 2 |  | Not Started | Hoang | Fields: resourceAccessed, authCheckPresent, authCheckLocation, principalVerified; enables IDOR + missing auth guard detection
3.M3.T5 | Semantic summary schema — logic-flaw vulnerability class | TASK | [5 empty] | 2 |  | Not Started | Hoang | Fields: businessConstraints[], stateTransitions[], enforcedAtBoundary; targets business logic and state machine flaws
3.M3.T6 | Function-level semantic abstraction generation (Python worker call) | TASK | [5 empty] | 2.5 |  | Not Started | Hoang | For each FunctionContext in call chain: call Python worker with `summarize` type; assemble into SummarizedCallChain struct
3.M3.T7 | Token footprint measurement before/after summarization | TASK | [5 empty] | 1.5 |  | Not Started | Hoang | Count tokens in raw call chain vs summarized version; target >= 60% token reduction; log in docs/benchmarks/token_footprint.md
3.M3.T8 | Multi-function vulnerability detection test (IDOR + missing auth guard) | TASK | [5 empty] | 1.7 |  | Not Started | Hoang | Synthetic test: IDOR case spanning caller (no auth check) + surface (uses external ID) + callee (DB lookup); assert detected
3.M4 | Token Budget Controller + LLM ReAct Scan + Scan Security Context Store | MILESTONE | 2026-07-31 | 2026-08-01 | 14 | 22 | 36 | 23 |  | Not Started |  | T7-T9 are SCSS — explicit DROP CANDIDATES; cut these first if window is tight; ReAct scan works without SCSS
3.M4.T1 | Surface prioritization ranking (CVE score x classifier uncertainty) | TASK | [5 empty] | 2.5 |  | Not Started | Hoang | Rank uncertain surfaces: (CVSS score from OSV x (1 - classifier confidence)); highest ranked consume token budget first
3.M4.T2 | Hard per-scan token cap enforcement | TASK | [5 empty] | 2 |  | Not Started | Hoang | Configurable cap (default: 50K tokens per scan); token counter incremented on each LLM call; halt when cap reached
3.M4.T3 | ReAct loop — Thought step | TASK | [5 empty] | 2.5 |  | Not Started | Hoang | LLM receives: semantic summary + vulnerability class schema; produces Thought: hypothesis + what additional context needed
3.M4.T4 | ReAct loop — context-request step (call chain depth + CVE lookup) | TASK | [5 empty] | 3 |  | Not Started | Hoang | LLM can request: deeper call chain (up to depth 3), CVE DB lookup from OSV-Scanner, or prior inferences from SCSS
3.M4.T5 | ReAct loop — Observation -> verdict step | TASK | [5 empty] | 2.5 |  | Not Started | Hoang | Max 3 ReAct steps; final step produces verdict; XGrammar enforces JSON schema; write to Finding channel
3.M4.T6 | XGrammar schema enforcement on ReAct output (extend Python worker) | TASK | [5 empty] | 2 |  | Not Started | Hoang | Add `llm_scan` type to Python worker dispatcher; XGrammar JSON schema for ReAct verdict
3.M4.T7 | [SCSS DROP FIRST] Scan Security Context Store: in-memory key-value store per scan | TASK | [5 empty] | 3 |  | Not Started | Hoang | DROP if M3.4 starts late; per-scan map: {surfaceID -> SecurityInference}; stores inferred data sources, sanitizer gaps
3.M4.T8 | [SCSS DROP FIRST] SCSS read/write hooks on LLM calls | TASK | [5 empty] | 2 |  | Not Started | Hoang | DROP if M3.4 starts late; before ReAct Thought: inject prior inferences from SCSS; after verdict: write new inferences
3.M4.T9 | [SCSS DROP FIRST] Cross-surface vulnerability detection test | TASK | [5 empty] | 3.5 |  | Not Started | Hoang | DROP if M3.4 starts late; test: vulnerability only detectable by combining inferences from two separate surfaces
3.BUF | G3 Buffer | BUFFER | 2026-07-21 | 2026-08-01 |  |  |  | 8 |  |  |  | Compressed 10% buffer (tight window); SCSS drop saves 8.5h — treat as de-facto buffer extension if M3.4 runs short

## G4 - Integration
ZeroTrust.sh · G4 — Integration, Report & Demo
Intern: Ton Minh Hoang · VNG ZingPlay Studio · Goal: Dedup + SSVC scoring + HTML report + end-to-end demo · Deadline: 2026-08-06
ID | Name | Type | Start Date | End Date | PERT O (h) | PERT ML (h) | PERT P (h) | PERT E (h) | Actual Hrs | Status | Owner | Notes
4.M1 | Dedup + SSVC Confidence Scoring | MILESTONE | 2026-08-01 | 2026-08-03 | 6 | 10 | 16 | 10.3 |  | Not Started |  | Skeleton should be pre-stubbed during G3 final week; merges Path A + Path B findings into unified 5-tier output
4.M1.T1 | Dedup — AST edit distance comparison | TASK | [5 empty] | 2 |  | Not Started | Hoang | Compare evidence snippets from Path A and Path B; collapse duplicates above edit-distance threshold
4.M1.T2 | Dedup — CWE pattern hash | TASK | [5 empty] | 1.5 |  | Not Started | Hoang | Hash: CWE ID + file path + line range; collapse findings with identical hash; fastest dedup pass, runs first
4.M1.T3 | Dedup — LLM semantic similarity check (Python worker call) | TASK | [5 empty] | 2 |  | Not Started | Hoang | For findings not collapsed by T1/T2: embed + cosine similarity; collapse if similarity > threshold
4.M1.T4 | SSVC dimension mapping -> 5-tier score assignment | TASK | [5 empty] | 2 |  | Not Started | Hoang | Dimensions: Exploitation (EPSS from OSV), Automatable (taint path), Technical Impact (sink type); map to BLOCK/HIGH/MEDIUM/LOW/SUPPRESSED
4.M1.T5 | Cross-path confirmation boost (+15% for findings confirmed by both paths) | TASK | [5 empty] | 1 |  | Not Started | Hoang | If same finding appears in Path A and Path B output (after dedup): boost SSVC score by +15%
4.M1.T6 | Suppression rules + dedup test suite | TASK | [5 empty] | 1.8 |  | Not Started | Hoang | Suppress: findings in test files (_test.go, test_*.py), framework-safe functions; test suite: 5+ dedup cases, 3+ suppression
4.M2 | HTML Report Generator + Patch Suggestions | MILESTONE | 2026-08-03 | 2026-08-04 | 6 | 10 | 16 | 10.3 |  | Not Started |  | Go html/template + embed only — no Python dependency; output is a single portable .html file
4.M2.T1 | Go html/template structure + embed setup | TASK | [5 empty] | 3 |  | Not Started | Hoang | //go:embed templates/*; base template with header, severity sections, finding cards; CSS inlined; no CDN dependencies
4.M2.T2 | Finding list serialization to HTML (severity groups, collapsible evidence panels) | TASK | [5 empty] | 2 |  | Not Started | Hoang | Group findings by SSVC tier (BLOCK first); each finding card: file + line, CWE, rationale, evidence snippet, patch suggestion
4.M2.T3 | Filter/sort controls (vanilla JS — no framework) | TASK | [5 empty] | 2.5 |  | Not Started | Hoang | Filter by: severity tier, CWE, file path; sort by: SSVC score, file name; ~50 lines of vanilla JS; self-contained
4.M2.T4 | SSVC score visualization (severity tier badges + dimension breakdown) | TASK | [5 empty] | 1 |  | Not Started | Hoang | Colored badge per tier (BLOCK=red, HIGH=orange, MEDIUM=yellow, LOW=blue, SUPPRESSED=grey); tooltip shows SSVC dimensions
4.M2.T5 | Patch suggestion prompt template + unified diff output (Python worker call) | TASK | [5 empty] | 1.8 |  | Not Started | Hoang | Zero-shot LLM call via `patch_suggest` type; prompt: finding rationale + code context; output: unified diff
4.M3 | End-to-End Demo Run + Hardening | MILESTONE | 2026-08-04 | 2026-08-06 | 6 | 10 | 16 | 10.3 |  | Not Started |  | Final gate before demo; `zerotrust scan ./target` must work end-to-end; timing must be < 10 min on test codebase
4.M3.T1 | Source or build 2-3 realistic AI-generated vulnerable codebases | TASK | [5 empty] | 2.5 |  | Not Started | Hoang | Languages: Python (FastAPI/Flask), Go (net/http), Java (Spring Boot); use real AI-agent-generated code where possible
4.M3.T2 | Full pipeline run on each target codebase | TASK | [5 empty] | 2 |  | Not Started | Hoang | Run `zerotrust scan ./target` end-to-end; verify: GGUF verified at startup, dirty files only re-scanned, HTML report generated
4.M3.T3 | Integration break fixes | TASK | [5 empty] | 2 |  | Not Started | Hoang | Resolve any pipeline failures from T2; if a fix exceeds 2h, escalate as At Risk; do not introduce new features
4.M3.T4 | Scan timing measurement (wall clock + per-component breakdown) | TASK | [5 empty] | 1 |  | Not Started | Hoang | Instrument: CPG build time, classifier gate time, LLM call time, total wall clock; target total < 10 min
4.M3.T5 | Demo script + rehearsal run | TASK | [5 empty] | 2.8 |  | Not Started | Hoang | Script covers: detection found, cost funnel % reached LLM, SSVC score explanation, patch diff, model integrity demo
4.M4 | PoE Layer — Red Team Agent + Docker Sandbox | STRETCH | 2026-08-04 | 2026-08-06 |  |  |  | 15 |  | Not Started |  | STRETCH — CUT FIRST. Do not attempt if any G3 M3.4 task is incomplete on Aug 1. Parallel with M4.3 if attempted.
4.M4.T1 | [STRETCH] LangGraph workflow setup (Recon -> Exploit -> Verify graph nodes) | TASK | [5 empty] | 4 |  | Not Started | Hoang | Python LangGraph v1.0; 3 nodes with typed state: Reconnaissance, Exploitation, Verification; state machine transitions
4.M4.T2 | [STRETCH] Docker sandbox: container spec + seccomp profile (network isolation) | TASK | [5 empty] | 3.5 |  | Not Started | Hoang | Go Docker SDK; container: no network, no root, seccomp deny-list; volume mount: target codebase read-only
4.M4.T3 | [STRETCH] Docker sandbox: attempt-trigger logic for BLOCK/HIGH findings | TASK | [5 empty] | 3.5 |  | Not Started | Hoang | LangGraph Exploitation node generates exploit code; passes to sandbox; captures execution result; timeout = 30s
4.M4.T4 | [STRETCH] Two-layer PoE output (technical trace + executive summary) | TASK | [5 empty] | 2.5 |  | Not Started | Hoang | Technical trace: exploit code, execution log, sandbox exit code; executive summary: vulnerability name, business impact
4.M4.T5 | [STRETCH] Static-evidence fallback when sandbox execution fails | TASK | [5 empty] | 1.5 |  | Not Started | Hoang | If sandbox exits non-zero or times out: emit 'Static evidence only — sandbox execution failed'; degrade gracefully
4.BUF | G4 Buffer | BUFFER | 2026-08-01 | 2026-08-06 |  |  |  | 3 |  |  |  | Tight 10% buffer; primary absorption: integration breaks in M4.3; if M4.4 not attempted, its 15h become additional buffer

## Research
ZeroTrust.sh · Scientific Research & Architecture Validation
Intern: Ton Minh Hoang · VNG ZingPlay Studio · Goal: Evidence-backed architecture validation · Runs Jun 9 – Aug 1
ID | Name | Type | Start Date | End Date | PERT O (h) | PERT ML (h) | PERT P (h) | PERT E (h) | Actual Hrs | Status | Owner | Notes
R.M1 | Literature Foundation | MILESTONE | 2026-06-09 | 2026-06-20 | 20 | 41 | 82 | 44.33 |  | In Progress |  | Read and annotate all 40 catalogued papers across 7 areas. Build paper-to-architecture-component linkage map.
R.M1.T1 | Read and annotate Area 1 (Deep Learning & ML for Vulnerability Detection, ~4 papers) and Area 2 (GNN for Vulnerability Detection, ~6 papers) | TASK | [5 empty] | 8.67 |  | In Progress | Hoang
R.M1.T2 | Read and annotate Area 3 (LLM for Code Security Analysis, ~6 papers) | TASK | [5 empty] | 12.67 |  | Not Started | Hoang
R.M1.T3 | Read and annotate Area 4 (Hybrid Static Analysis + LLM, ~5 papers) and Area 5 (AI-Generated Code Security & Prompt Injection, ~5 papers) | TASK | [5 empty] | 10.83 |  | Not Started | Hoang
R.M1.T4 | Read and annotate Area 6 (Token Cost Optimization, ~4 papers) and Area 7 (Call Graph, Taint Analysis & Code Representations, ~10 papers) | TASK | [5 empty] | 9 |  | Not Started | Hoang
R.M1.T5 | Build paper-to-architecture-component linkage map: assign each of the 40 papers to >= 1 ZeroTrust.sh component as primary evidence | TASK | [5 empty] | 3.17 |  | Not Started | Hoang
R.M2 | Architecture Validation Matrix | MILESTONE | 2026-06-16 | 2026-06-27 | 4 | 8.5 | 21 | 9.83 |  | Not Started |  | Map every architecture component to >= 1 supporting paper. Flag components with no academic backing as validation gaps.
R.M2.T1 | Map Differential Indexer and all Path A sub-components to >= 1 supporting paper each | TASK | [5 empty] | 2.33 |  | Not Started | Hoang
R.M2.T2 | Map Path B three-tier cost funnel to supporting papers with specific claimed performance figures recorded | TASK | [5 empty] | 2.33 |  | Not Started | Hoang
R.M2.T3 | Map Dedup layer and 5-tier Confidence Scoring to supporting papers | TASK | [5 empty] | 1.25 |  | Not Started | Hoang
R.M2.T4 | Map Proof-of-Exploit Layer to supporting papers on automated vulnerability verification | TASK | [5 empty] | 1.75 |  | Not Started | Hoang
R.M2.T5 | Identify every architecture component with zero academic backing and document each as an open validation gap | TASK | [5 empty] | 2.17 |  | Not Started | Hoang
R.M3 | Benchmark & Performance Claims Verification | MILESTONE | 2026-06-23 | 2026-07-04 | 3 | 6.5 | 18 | 7.83 |  | Not Started |  | Verify every quantitative claim in the architecture docs against its source paper.
R.M3.T1 | Verify UniXcoder-Base-Nine F1=94.73% on BigVul: locate original paper, confirm exact evaluation setup | TASK | [5 empty] | 1.25 |  | Not Started | Hoang
R.M3.T2 | Verify 88-93% false positive reduction claim for the LLM Verifier | TASK | [5 empty] | 1.75 |  | Not Started | Hoang
R.M3.T3 | Verify ~80-95% cost reduction claim for the Differential Indexer | TASK | [5 empty] | 1.25 |  | Not Started | Hoang
R.M3.T4 | Verify ~15-25% LLM escalation rate and ~95% file elimination rate | TASK | [5 empty] | 1.25 |  | Not Started | Hoang
R.M3.T5 | Compile benchmarks reference table: claim text, source, confidence level, follow-up action | TASK | [5 empty] | 2.33 |  | Not Started | Hoang
R.M4 | Competitive Landscape Research | MILESTONE | 2026-06-30 | 2026-07-11 | 6 | 12 | 26 | 13.33 |  | Not Started |  | Research Semgrep, Snyk Code, and CodeRabbit structural gaps vs ZeroTrust.sh. Compile differentiation evidence table.
R.M4.T1 | Research publicly available accuracy and precision data for Semgrep OSS and Semgrep Pro | TASK | [5 empty] | 2.33 |  | Not Started | Hoang
R.M4.T2 | Research Snyk Code architecture with focus on cloud dependency and source-code-upload requirements | TASK | [5 empty] | 2.17 |  | Not Started | Hoang
R.M4.T3 | Research CodeRabbit's PR-gated workflow architecture: document what it structurally cannot do | TASK | [5 empty] | 2.17 |  | Not Started | Hoang
R.M4.T4 | Search academic databases for evidence that local-only execution with AI-specific threat detection is under-served | TASK | [5 empty] | 4.5 |  | Not Started | Hoang
R.M4.T5 | Compile differentiation evidence table: ZeroTrust.sh differentiator, evidence source, competitor, gap type | TASK | [5 empty] | 2.17 |  | Not Started | Hoang
R.M5 | Architecture Justification Document | MILESTONE | 2026-07-07 | 2026-07-25 | 6.5 | 13 | 30 | 14.75 |  | Not Started |  | Formal document linking every major design decision to research evidence. Written for tech lead + stakeholders.
R.M5.T1 | Write Path A justification section: Semgrep + CodeQL/Joern + LLM Verifier rationale with paper citations | TASK | [5 empty] | 2.33 |  | Not Started | Hoang
R.M5.T2 | Write Path B justification section: cost-funnel rationale for each tier with paper citations | TASK | [5 empty] | 4.5 |  | Not Started | Hoang
R.M5.T3 | Write Dedup and 5-tier Confidence Scoring justification with triple-path fusion rationale | TASK | [5 empty] | 2.33 |  | Not Started | Hoang
R.M5.T4 | Write Differential Indexer justification: hash-based incremental scanning design | TASK | [5 empty] | 1.25 |  | Not Started | Hoang
R.M5.T5 | Write PoE Layer justification and compile tech-lead narrative summary (<=2 pages for non-technical stakeholders) | TASK | [5 empty] | 4.33 |  | Not Started | Hoang
R.M6 | Ongoing Research Monitoring | MILESTONE | 2026-07-14 | 2026-08-01 | 3.5 | 8.5 | 19 | 9.42 |  | Not Started |  | Set up alert infrastructure for post-June-2026 papers. Forward-citation pass on top 5 most-cited papers.
R.M6.T1 | Configure arXiv email digest alerts for all 7 research areas using category filters cs.CR, cs.SE, cs.LG | TASK | [5 empty] | 1.08 |  | Not Started | Hoang
R.M6.T2 | Configure Google Scholar keyword alerts for ZeroTrust.sh-relevant terms | TASK | [5 empty] | 1.08 |  | Not Started | Hoang
R.M6.T3 | Perform forward-citation pass on top 5 most-cited papers in the 40-paper catalogue | TASK | [5 empty] | 3.33 |  | Not Started | Hoang
R.M6.T4 | Write monitoring runbook documenting exact search queries, weekly review steps, monthly deep-search protocol | TASK | [5 empty] | 2.17 |  | Not Started | Hoang
R.M6.T5 | Integrate newly discovered papers into validation matrix; update benchmarks reference table if figures superseded | TASK | [5 empty] | 1.75 |  | Not Started | Hoang

## Research Papers
ZeroTrust.sh · Research Paper Manager
Smart Paper Manager · Use column dropdowns (▾) to filter by Category, Tags, Read Status · Click any column header to sort · Write your notes in column K
# | Title | Authors | Year | Venue | Category | Tags | Read Status | Relevance to ZeroTrust.sh | URL | Literature Review Notes
1 | Automated Vulnerability Detection in Source Code Using Deep Representation Learning | Feng et al. | 2026 | arXiv | ML/DL Detection | CNN, deep representation learning, source code, vulnerability classifier | Unread | CNN-based deep representation learning for vulnerability detection — validates ML classifier gate in Path B Tier 2 | https://arxiv.org/abs/2602.23121 | Write your notes here…
2 | DiverseVul: A New Vulnerable Source Code Dataset for Deep Learning Based Vulnerability Detection | Jia et al. | 2023 | RAID 2023 / ACM | ML/DL Detection | dataset, C/C++, CWE, BigVul alternative, training data, benchmark, 18945 functions | Unread | Largest diverse C/C++ vulnerability dataset (18,945 functions, 150 CWEs) — training data source for Code Vulnerability Classifier | https://arxiv.org/abs/2304.00409 | Write your notes here…
3 | Vulnerability Detection in C/C++ Code with Deep Learning | Multiple authors | 2024 | arXiv | ML/DL Detection | neural network, program slicing, C/C++, deep learning | Unread | Neural networks with program slices for vulnerability detection — informs Tier 2 classifier design | https://arxiv.org/abs/2405.12384 | Write your notes here…
4 | Deep Learning Aided Software Vulnerability Detection: A Survey | Survey authors | 2025 | arXiv | ML/DL Detection | survey, deep learning, vulnerability detection, baseline comparison | Unread | Comprehensive DL survey for vulnerability detection — baseline reference for Tier 2 classifier selection | https://arxiv.org/abs/2503.04002 | Write your notes here…
5 | Software Vulnerability Detection Using a Lightweight Graph Neural Network (VulGNN) | Zhu et al. | 2026 | arXiv | Graph Neural Networks | GNN, lightweight, LLM-parity, local inference, classifier, small model | Unread | Lightweight GNN achieving LLM-parity at 100x smaller size — validates cheap local classifier concept in new architecture | https://arxiv.org/abs/2603.29216 | Write your notes here…
6 | Vul-LMGNNs: Fusing Language Models and Graph Neural Networks for Code Vulnerability Detection | Rong et al. | 2024 | arXiv | Graph Neural Networks | GNN, language model, hybrid, code representation, code LM | Unread | Hybrid code LM + GNN — informs Call Graph + Classifier integration in Path B Tier 2 | https://arxiv.org/abs/2404.14719 | Write your notes here…
7 | Structure-Aware Code Vulnerability Analysis With Graph Neural Networks | Allamanis et al. | 2024 | arXiv | Graph Neural Networks | GNN, Java, structure-aware, vulnerability fixing, commit-level | Unread | GNN-based vulnerability analysis using Java vulnerability-fixing commits — informs structure-aware detection | https://arxiv.org/abs/2307.11454 | Write your notes here…
8 | Graph Neural Networks for Vulnerability Detection: A Counterfactual Explanation | Li et al. | 2024 | arXiv | Graph Neural Networks | GNN, explainability, counterfactual, confidence scoring, interpretability | Unread | Explainability analysis of GNN detection — informs confidence scoring in Dedup layer | https://arxiv.org/abs/2404.15687 | Write your notes here…
9 | ReGVD: Revisiting Graph Neural Networks for Vulnerability Detection | Nguyen et al. | 2022 | ACM/IEEE | Graph Neural Networks | GNN, token sequence, baseline, benchmark, foundational | Unread | Foundational GNN model treating source code as flat token sequences — baseline for Tier 2 classifier | https://dl.acm.org/doi/abs/10.1145/3510454.3516865 | Write your notes here…
10 | LineVD: Statement-level Vulnerability Detection using Graph Neural Networks | Chen et al. | 2022 | arXiv | Graph Neural Networks | GNN, statement-level, line localization, fine-grained, HTML report | Unread | Fine-grained GNN vulnerability localization — informs line-level finding output in HTML report | https://arxiv.org/abs/2203.05181 | Write your notes here…
11 | LLMs in Code Vulnerability Analysis: A Proof of Concept | Kochling et al. | 2026 | arXiv | LLM Code Analysis | LLM, empirical, proof-of-concept, zero-shot, Path B validation | Unread | Empirical PoC for LLM vulnerability analysis — validates LLM Semantic Scan role in Path B Tier 3 | https://arxiv.org/abs/2601.08691 | Write your notes here…
12 | IRIS: LLM-Assisted Static Analysis for Detecting Security Vulnerabilities | Scanlon et al. | 2024 | arXiv | LLM Code Analysis | hybrid SAST+LLM, false positive, 80% FP reduction, IRIS, key paper | Unread | Hybrid SAST+LLM detecting 55/120 vulns + 6 new, reducing FP by 80% — directly validates ZeroTrust.sh hybrid design | https://arxiv.org/abs/2405.17238 | Write your notes here…
13 | Large Language Model for Vulnerability Detection and Repair: Literature Review and the Road Ahead | Zhang et al. | 2025 | ACM TOSEM | LLM Code Analysis | survey, LLM, vulnerability repair, patch generation, comprehensive review | Unread | Comprehensive LLM vulnerability + repair survey — informs patch generation design across all approaches | https://dl.acm.org/doi/10.1145/3708522 | Write your notes here…
14 | Understanding the Effectiveness of LLMs in Detecting Security Vulnerabilities | Steenhoek et al. | 2023 | arXiv | LLM Code Analysis | LLM, prompting strategy, systematic evaluation, false positive, prompt design | Unread | Systematic LLM evaluation with prompting strategy analysis — informs LLM Verifier prompt design in Path A | https://arxiv.org/abs/2311.16169 | Write your notes here…
15 | Large Language Models for Source Code Analysis: Applications, Models and Datasets | Sharma et al. | 2025 | arXiv | LLM Code Analysis | survey, LLM architectures, code analysis, model selection, datasets | Unread | Survey of LLM architectures for code analysis — model selection reference for LLM components | https://arxiv.org/abs/2503.17502 | Write your notes here…
16 | Can Large Language Models Find And Fix Vulnerable Software? | Pearce et al. | 2023 | arXiv | LLM Code Analysis | LLM, detection, repair, empirical evaluation, fix generation | Unread | Empirical evaluation of LLM detection + repair — validates dual-role LLM use in Approaches 2 and 3 | https://arxiv.org/abs/2308.10345 | Write your notes here…
17 | LLM-Driven SAST-Genius: A Hybrid Static Analysis Framework for Comprehensive and Actionable Security | Multiple authors | 2024 | arXiv | Hybrid SAST+LLM | hybrid, SAST+LLM, false positive, 91% FP reduction, Semgrep, key paper | Unread | Hybrid SAST+LLM reducing FP by 91% (225→20 alerts) vs Semgrep alone — strongest validation of ZeroTrust.sh architecture | https://arxiv.org/abs/2509.15433 | Write your notes here…
18 | ZeroFalse: Improving Precision in Static Analysis with LLMs | Scanlon et al. | 2024 | arXiv | Hybrid SAST+LLM | LLM, false positive reduction, static analysis, precision, ZeroFalse | Unread | LLM false positive reduction in static analysis — validates LLM Verifier design in Path A | https://arxiv.org/abs/2510.02534 | Write your notes here…
19 | Combining Large Language Models with Static Analyzers for Code Review Generation | Jaoua et al. | 2025 | arXiv | Hybrid SAST+LLM | LLM, static analysis, code review, patch suggestion, output format | Unread | LLM + static analysis for code review — informs patch suggestion output format | https://arxiv.org/abs/2502.06633 | Write your notes here…
20 | A Contemporary Survey of LLM-Assisted Program Analysis | Survey authors | 2025 | arXiv | Hybrid SAST+LLM | survey, program analysis, LLM, comprehensive, all approaches reference | Unread | Comprehensive survey of LLM program analysis techniques — architecture reference for all three approaches | https://arxiv.org/abs/2502.18474 | Write your notes here…
21 | RepoAudit: An Autonomous LLM-Agent for Repository-Level Code Auditing | Li et al. | 2025 | arXiv | Hybrid SAST+LLM | LLM agent, repository-level, multi-agent, orchestration, Approach 3 | Unread | LLM-agent for repo-level auditing — informs Approach 3 multi-agent orchestration design | https://arxiv.org/abs/2501.18160 | Write your notes here…
22 | Security Vulnerabilities in AI-Generated Code: A Large-Scale Analysis of Public GitHub Repositories | Zhao et al. | 2024 | IEEE/ACM | AI-Generated Code Security | AI-generated code, CWE, GitHub, empirical, 4241 instances, market validation | Unread | 4,241 CWE instances across AI-generated code from 4 tools — empirical validation of the core ZeroTrust.sh problem statement | https://arxiv.org/abs/2510.26103 | Write your notes here…
23 | Prompt Injection Attacks on Agentic Coding Assistants: A Systematic Analysis | Yang et al. | 2026 | arXiv | AI Agent Security | prompt injection, agentic, coding assistant, attack, 85% success rate | Unread | 85%+ attack success rates for prompt injection in agentic assistants — validates ZeroTrust.sh AI-specific threat detection | https://arxiv.org/abs/2601.17548 | Write your notes here…
24 | Security Degradation in Iterative AI Code Generation: A Systematic Analysis of the Paradox | Multiple authors | 2025 | IEEE-ISTAS | AI-Generated Code Security | iterative generation, vibe-coding, security degradation, LLM, threat model | Unread | Iterative LLM interactions without human review introduce new vulnerabilities — validates vibe-coding threat model | https://arxiv.org/abs/2506.11022 | Write your notes here…
25 | Assessing the Quality and Security of AI-Generated Code: A Quantitative Analysis | Multiple authors | 2024 | arXiv | AI-Generated Code Security | AI-generated code, quantitative, security assessment, quality metrics | Unread | Quantitative security analysis of AI-generated code — market validation and threat taxonomy reference | https://arxiv.org/abs/2508.14727 | Write your notes here…
26 | You Still Have to Study: On the Security of LLM Generated Code | Ferrara et al. | 2024 | arXiv | AI-Generated Code Security | Copilot, CWE, 36-40% vulnerability rate, LLM-generated code, pitch statistic | Unread | 36–40% of Copilot code contains CWE vulnerabilities — key statistic for product positioning and pitch | https://arxiv.org/abs/2408.07106 | Write your notes here…
27 | FrugalGPT: How to Use Large Language Models While Reducing Cost and Improving Performance | Eisingerich et al. | 2023 | arXiv | Token Cost Optimization | cascade routing, cost optimization, 98% savings, LLM pipeline, FrugalGPT | Unread | Cascade routing achieving 98% cost savings — theoretical foundation for Cascading Intelligence architecture | https://arxiv.org/abs/2305.05176 | Write your notes here…
28 | Batch Prompting: Efficient Inference with Large Language Model APIs | Rajkumar et al. | 2023 | arXiv | Token Cost Optimization | batch processing, token cost, 5x reduction, inference efficiency | Unread | Batch processing reducing LLM token costs up to 5x — informs Token Budget Controller batching strategy | https://arxiv.org/abs/2301.08721 | Write your notes here…
29 | Token Sugar: Making Source Code Sweeter for LLMs through Token-Efficient Shorthand | Multiple authors | 2025 | arXiv | Token Cost Optimization | token optimization, code representation, shorthand, context compression | Unread | Token optimization for code representation — informs context chunking in Token Budget Controller | https://arxiv.org/abs/2512.08266 | Write your notes here…
30 | Learning to Focus: Context Extraction for Efficient Code Vulnerability Detection with Language Models | Dittmann et al. | 2025 | arXiv | Token Cost Optimization | context filtering, token budget, vulnerability detection, efficiency, focus extraction | Unread | Context filtering for reducing LLM token consumption in vulnerability detection — directly validates Token Budget Controller | https://arxiv.org/abs/2505.17460 | Write your notes here…
31 | Vulnerability Detection with Interprocedural Context in Multiple Languages: Assessing Effectiveness and Cost | Gharibi et al. | 2024 | arXiv | Call Graph & Taint Analysis | interprocedural, multi-language, call graph, LLM detection, effectiveness | Unread | Interprocedural analysis impact on LLM detection across languages — validates Call Graph + CVE Enrichment in Path B | https://arxiv.org/abs/2604.08417 | Write your notes here…
32 | Multi-Agent Taint Specification Extraction for Vulnerability Detection | Zhang et al. | 2026 | arXiv | Call Graph & Taint Analysis | taint analysis, multi-agent, CodeQL, LLM, Approach 3 | Unread | Multi-agent LLM + taint analysis — informs Approach 3 multi-agent architecture with CodeQL/Joern integration | https://arxiv.org/abs/2601.10865 | Write your notes here…
33 | LLMxCPG: Context-Aware Vulnerability Detection Through Code Property Graph-Guided LLMs | Pan et al. | 2024 | arXiv | Call Graph & Taint Analysis | CPG, code property graph, context-aware, LLM, Path B integration | Unread | CPG-guided LLM for context-aware detection — informs CPG integration in Path B call graph analysis | https://arxiv.org/abs/2507.16585 | Write your notes here…
34 | Bridging Code Property Graphs and Language Models for Program Analysis | Mahfouz et al. | 2026 | arXiv | Call Graph & Taint Analysis | CPG, LLM, program analysis, hybrid CPG+LLM, framework | Unread | Framework bridging CPG and LLMs — validates hybrid CPG+LLM design in Path B | https://arxiv.org/abs/2603.24837 | Write your notes here…
35 | Enhancing Software Vulnerability Detection Using Code Property Graphs and Convolutional Neural Networks | Multiple authors | 2025 | arXiv | Call Graph & Taint Analysis | CPG, CNN, local structure, global structure, code classifier training | Unread | CPG+CNN for local and global code structure — informs Code Classifier training in new architecture | https://arxiv.org/abs/2503.18175 | Write your notes here…
36 | VulTrLM: LLM-Assisted Vulnerability Detection via AST Decomposition and Comment Enhancement | Liu et al. | 2025 | Empirical Software Engineering | Call Graph & Taint Analysis | LLM, AST decomposition, semantic enhancement, comment, AST preprocessing | Unread | LLM-assisted AST decomposition for semantic enhancement — informs AST preprocessing in Path B Tier 1 | https://dl.acm.org/doi/10.1007/s10664-025-10738-7 | Write your notes here…
37 | Dataflow Analysis-Inspired Deep Learning for Efficient Vulnerability Detection | Cheng et al. | 2022 | arXiv | Call Graph & Taint Analysis | dataflow analysis, deep learning, CodeQL integration, Path A validation | Unread | Dataflow analysis-inspired DL approach — validates dataflow integration in Path A CodeQL/Joern | https://arxiv.org/abs/2212.08108 | Write your notes here…
38 | Reducing False Positives in Static Bug Detection with LLMs: An Empirical Study in Industry | Dittmann et al. | 2026 | arXiv | Hybrid SAST+LLM | false positive, LLM, industrial study, production scale, empirical | Unread | Industrial study on LLM false positive reduction — validates LLM Verifier design in Path A at production scale | https://arxiv.org/abs/2601.18844 | Write your notes here…
39 | LSAST: Enhancing Cybersecurity through LLM-supported Static Application Security Testing | Multiple authors | 2024 | arXiv | Local LLM Deployment | local LLM, privacy-first, offline, SAST, no cloud API, on-device | Unread | Locally-hostable LLM for SAST without cloud APIs — validates privacy-first local LLM deployment approach | https://arxiv.org/abs/2409.15735 | Write your notes here…
40 | Software Vulnerability Analysis Across Programming Language and Program Representation Landscapes: A Survey | Multiple authors | 2025 | arXiv | Call Graph & Taint Analysis | survey, AST, CFG, PDG, CPG, program representation, multi-language | Unread | Survey of AST, CFG, PDG, CPG representations — reference for program representation selection across all approaches | https://arxiv.org/abs/2503.20244 | Write your notes here…
41 | We Have a Package for You! A Comprehensive Analysis of Package Hallucinations by Code Generating LLMs | Spracklen et al. | 2024 | USENIX Security 2025 | AI Agent Security | slopsquatting, package hallucination, supply chain, npm, pip, 205474 hallucinations, foundational | Unread | Foundational study: 205,474 hallucinated package names across 16 LLMs — commercial at 5.2%, open-source at 21.7%. Baseline threat ZeroTrust.sh must detect. | https://arxiv.org/abs/2406.10279 | Write your notes here…
42 | Importing Phantoms: Measuring LLM Package Hallucination Vulnerabilities | Krishna et al. | 2025 | arXiv:2501.19012 | AI Agent Security | slopsquatting, package hallucination, language comparison, model size, Pareto frontier | Unread | Hallucination rates across languages, model sizes, and task specificity — identifies highest-risk agent configurations for slopsquatting detection. | https://arxiv.org/abs/2501.19012 | Write your notes here…
43 | The Range Shrinks, the Threat Remains: Re-evaluating LLM Package Hallucinations on the 2026 Frontier-Model Cohort | Multiple authors | 2026 | arXiv:2605.17062 | AI Agent Security | slopsquatting, frontier models, Claude, GPT-5, 127 common hallucinations, 2026 benchmark | Unread | Frontier models (Claude Haiku 4.5 at 4.62%, GPT-5.4-mini at 6.10%) still hallucinate; 127 package names all models invent — rich target set for detection rules. | https://arxiv.org/abs/2605.17062 | Write your notes here…
44 | PackMonitor: Enabling Zero Package Hallucinations Through Decoding-Time Monitoring | Liu et al. | 2026 | arXiv:2602.20717 | AI Agent Security | slopsquatting, decoding-time defense, PyPI, npm, authoritative package list, prevention | Unread | Defense via decoding-time intervention constraining generation to authoritative package lists — informs ZeroTrust.sh's detection and verification strategy. | https://arxiv.org/abs/2602.20717 | Write your notes here…
45 | Secure or Suspect? Investigating Package Hallucinations of Shell Command in Original and Quantized LLMs | Haque et al. | 2025 | arXiv:2512.08213 | AI Agent Security | slopsquatting, quantized models, GGUF, shell command, realistic URL mimicry | Unread | Quantized models have significantly higher hallucination rates; fabricated packages mimic GitHub/golang.org URLs — relevant for sophisticated slopsquatting detection. | https://arxiv.org/abs/2512.08213 | Write your notes here…
46 | 'Your AI, My Shell': Demystifying Prompt Injection Attacks on Agentic AI Coding Editors | Liu et al. | 2025 | arXiv:2509.22040 | AI Agent Security | prompt injection, Cursor, repository poisoning, agentic editor, shell execution hijack | Unread | First empirical analysis of Cursor via repository poisoning — attackers inject malicious instructions into dev resources to hijack shell execution. Direct ZeroTrust.sh threat model. | https://arxiv.org/abs/2509.22040 | Write your notes here…
47 | The Dark Side of LLMs: Agent-based Attacks for Complete Computer Takeover | Lupinacci et al. | 2025 | arXiv:2507.06850 | AI Agent Security | privilege escalation, inter-agent trust, 94.4% vulnerable, agent-to-agent attack, safety bypass | Unread | 94.4% of models vulnerable to direct injection; 83.3% to inter-agent trust exploitation — key data for detecting agent-to-agent attack chains in ZeroTrust.sh. | https://arxiv.org/abs/2507.06850 | Write your notes here…
48 | VIGIL: Defending LLM Agents Against Tool Stream Injection via Verify-Before-Commit | Lin et al. | 2026 | arXiv:2601.05755 | AI Agent Security | tool stream injection, SIREN benchmark, verify-before-commit, runtime poisoning, 959 attack cases | Unread | Defense against tool stream injection; SIREN benchmark (959 attack cases) provides test corpus for ZeroTrust.sh detection validation. | https://arxiv.org/abs/2601.05755 | Write your notes here…
49 | Agentic AI Security: Threats, Defenses, Evaluation, and Open Challenges | Datta et al. | 2025 | arXiv:2510.23883 | AI Agent Security | survey, agentic AI, threat taxonomy, tool use, memory, autonomy, planning | Unread | Comprehensive survey of agentic AI threat taxonomy distinguishing autonomous execution risks from traditional LLM safety — essential scope reference for ZeroTrust.sh. | https://arxiv.org/abs/2510.23883 | Write your notes here…
50 | Are AI-assisted Development Tools Immune to Prompt Injection? | Multiple authors | 2026 | arXiv:2603.21642 | AI Agent Security | MCP, tool poisoning, Claude Code, Cursor, Cline, Continue, Gemini CLI, coding tools benchmark | Unread | First empirical analysis of MCP clients (Claude Code, Cursor, Cline, Continue, Gemini CLI) against tool-poisoning attacks — directly relevant to detecting injection in AI tool contexts. | https://arxiv.org/abs/2603.21642 | Write your notes here…
51 | Taming Various Privilege Escalation in LLM-Based Agent Systems: A Mandatory Access Control Framework | Multiple authors | 2026 | arXiv:2601.11893 | AI Agent Security | privilege escalation, MAC framework, SEAgent, formal model, agent security policy | Unread | Formal model of privilege escalation in LLM agents with SEAgent MAC framework — informs detection rules for trust boundary violations in agentic codebases. | https://arxiv.org/abs/2601.11893 | Write your notes here…
52 | BacAlarm: Mining and Simulating Composite API Traffic to Prevent Broken Access Control Violations | Multiple authors | 2025 | arXiv:2512.19997 | Logic Vuln Detection | broken access control, REST API, OWASP API, LLM agent, RAG, anomaly detection | Unread | Broken access control detection in REST APIs via LLM-based agent traffic simulation and ensemble anomaly detection — core to detecting authorization gaps in Path B. | https://arxiv.org/abs/2512.19997 | Write your notes here…
53 | Rethinking Broken Object Level Authorization Attacks Under Zero Trust Principle | Wu et al. | 2025 | arXiv:2507.02309 | Logic Vuln Detection | BOLA, IDOR, zero trust, resource ID dataflow, authorization interval, 35 new CVEs | Unread | BOLAZ: zero-trust defense for BOLA/IDOR via resource ID data flow analysis; discovered 35 new vulnerabilities — directly validates Path B's IDOR detection design. | https://arxiv.org/abs/2507.02309 | Write your notes here…
54 | VULSOLVER: Vulnerability Detection via LLM-Driven Constraint Solving | Li et al. | 2025 | arXiv:2509.00882 | Logic Vuln Detection | LLM, constraint solving, call-chain analysis, 96.29% accuracy, semantic reasoning | Unread | SAST + LLM semantic reasoning with progressive constraint modeling achieves 96.29% accuracy — applicable to detecting contextually-wrong authorization logic. | https://arxiv.org/abs/2509.00882 | Write your notes here…
55 | SAVANT: Vulnerability Detection in Application Dependencies through Semantic-Guided Reachability Analysis | Multiple authors | 2025 | arXiv:2506.17798 | Logic Vuln Detection | semantic preprocessing, LLM, reachability analysis, library API, 83.8% precision | Unread | Semantic preprocessing + LLM context analysis for vulnerable API patterns; 83.8% precision — relevant to detecting missing authorization checks in library calls. | https://arxiv.org/abs/2506.17798 | Write your notes here…
56 | Argus: Reorchestrating Static Analysis via a Multi-Agent Ensemble for Full-Chain Security Vulnerability Detection | Multiple authors | 2025 | arXiv:2604.06633 | Logic Vuln Detection | multi-agent, SAST, false positive reduction, multi-hop reasoning, zero-day, full-chain | Unread | First multi-agent LLM framework for SAST with multi-hop reasoning — discovers zero-day vulnerabilities spanning multiple functions; applicable to detecting business logic flaws. | https://arxiv.org/abs/2604.06633 | Write your notes here…
57 | Benchmarking LLMs and LLM-based Agents in Practical Vulnerability Detection for Code Repositories | Multiple authors | 2025 | ACL 2025 / arXiv:2503.03586 | Logic Vuln Detection | JitVul benchmark, 879 CVEs, interprocedural, ReAct agents, authorization flaws, ACL | Unread | JitVul benchmark (879 CVEs) requires interprocedural analysis; ReAct agents outperform LLMs on auth flaws — suggests agentic approaches for Path B's multi-function context. | https://arxiv.org/abs/2503.03586 | Write your notes here…
58 | Prompting the Priorities: A First Look at Evaluating LLMs for Vulnerability Triage and Prioritization | Multiple authors | 2025 | arXiv:2510.18508 | Logic Vuln Detection | SSVC, triage, prioritization, 384 real-world CVEs, risk surface selection, LLM evaluation | Unread | LLM evaluation on SSVC triage framework with 384 real-world vulnerabilities — methodology for prioritizing high-risk code surfaces before deep Path B analysis. | https://arxiv.org/abs/2510.18508 | Write your notes here…
59 | I Can't Believe It's Not a Valid Exploit | Multiple authors | 2026 | arXiv:2602.04165 | Logic Vuln Detection | PoC-Gym, exploit generation, static analysis guidance, 21% improvement, validation limits | Unread | PoC-Gym framework shows static analysis guidance improves LLM exploit generation by 21% — informs heuristics for filtering false-positive authorization scenarios in Path B. | https://arxiv.org/abs/2602.04165 | Write your notes here…
60 | Mind the Gap: A Practical Attack on GGUF Quantization | Egashira et al. | 2025 | ICML 2025 / arXiv:2505.23786 | Local LLM Deployment | GGUF, quantization, backdoor injection, Ollama, llama.cpp, supply chain, ICML | Unread | Backdoor injection via GGUF quantization errors — essential threat model for ZeroTrust.sh's local LLM deployment: quantized models can exhibit hidden malicious behaviors. | https://arxiv.org/abs/2505.23786 | Write your notes here…
61 | Widening the Gap: Exploiting LLM Quantization via Outlier Injection | Shi et al. | 2025 | arXiv:2605.15152 | Local LLM Deployment | quantization attack, AWQ, GPTQ, GGUF, outlier injection, adversarial, supply chain | Unread | First quantization-conditioned attack affecting AWQ/GPTQ/GGUF — demonstrates supply-chain risks in locally-deployed quantized models; complements GGUF threat model. | https://arxiv.org/abs/2605.15152 | Write your notes here…
62 | A First Look At Efficient And Secure On-Device LLM Inference Against KV Leakage | Yang et al. | 2024 | arXiv:2409.04040 | Local LLM Deployment | on-device LLM, KV cache leakage, FHE, TEE, privacy, local inference security | Unread | Privacy attacks on on-device LLM inference via KV cache leakage — demonstrates how local inference can leak conversation history; relevant to ZeroTrust.sh's privacy-first design. | https://arxiv.org/abs/2409.04040 | Write your notes here…
63 | A Cost-Benefit Analysis of On-Premise Large Language Model Deployment: Breaking Even with Commercial LLM Services | Pan et al. | 2025 | arXiv:2509.18101 | Local LLM Deployment | on-premise, cost analysis, breakeven, Qwen, Llama, Mistral, cloud vs local, value proposition | Unread | Quantifies breakeven for on-premise LLM vs cloud APIs — supports ZeroTrust.sh's value proposition: local deployment becomes cost-competitive at scale. | https://arxiv.org/abs/2509.18101 | Write your notes here…
69 | LLMLingua: Compressing Prompts for Accelerated Inference of Large Language Models | Jiang et al. | 2023 | arXiv:2310.05736 | Prompt Compression | prompt compression, token pruning, 20x compression, budget control, coarse-to-fine | Unread | Iterative token-level compression with budget control; up to 20x compression with minimal loss — directly applicable to compressing code context before LLM security scans. | https://arxiv.org/abs/2310.05736 | Write your notes here…
70 | LLMLingua-2: Data Distillation for Efficient and Faithful Task-Agnostic Prompt Compression | Jiang et al. | 2024 | arXiv:2403.12968 | Prompt Compression | prompt compression, data distillation, token classification, 3-6x faster, 1.6-2.9x latency | Unread | Compression as token classification via GPT-4 distillation; 3–6x faster than LLMLingua with 2–5x compression ratios — ideal for repeated scans of similar code patterns. | https://arxiv.org/abs/2403.12968 | Write your notes here…
71 | LongLLMLingua: Accelerating and Enhancing LLMs in Long Context Scenarios via Prompt Compression | Jiang et al. | 2023 | arXiv:2310.06839 | Prompt Compression | long context, question-aware compression, document reordering, 94% cost reduction, 4x fewer tokens | Unread | Question-aware compression for long-context scenarios; 94% cost reduction on LooGLE — critical for scanning large codebases and enriching prompts with vulnerability databases. | https://arxiv.org/abs/2310.06839 | Write your notes here…
72 | RECOMP: Improving Retrieval-Augmented LMs with Compression and Selective Augmentation | Xu et al. | 2023 | arXiv:2310.04408 | Prompt Compression | RAG, retrieval augmentation, extractive compression, abstractive compression, 6% compression rate | Unread | Compresses retrieved documents in RAG pipelines via extractive and abstractive methods — relevant when ZeroTrust.sh augments prompts with retrieved CVE or security knowledge. | https://arxiv.org/abs/2310.04408 | Write your notes here…
73 | Pruning the Unsurprising: Efficient LLM Reasoning via First-Token Surprisal | Multiple authors | 2025 | arXiv:2508.05988 | Prompt Compression | CoT compression, first-token surprisal, 23.5% token reduction, 43.5% latency reduction, ASAP | Unread | ASAP framework compresses chain-of-thought by 23.5% tokens and 43.5% latency — optimizes reasoning chains in vulnerability analysis without sacrificing accuracy. | https://arxiv.org/abs/2508.05988 | Write your notes here…
74 | Large Language Models as Optimizers (OPRO) | Yang et al. | 2023 | arXiv:2309.03409 | Prompt Engineering | automatic prompt optimization, OPRO, LLM-based refinement, in-context learning, 50% improvement | Unread | Automatic prompt optimization via LLM-based iterative refinement; best prompts beat human-designed by up to 50% — applicable to auto-tuning ZeroTrust.sh security scanning prompts. | https://arxiv.org/abs/2309.03409 | Write your notes here…
75 | Chain of Draft: Thinking Faster by Writing Less | Xu et al. | 2025 | arXiv:2502.18600 | Prompt Engineering | chain of draft, CoT efficiency, 7.6% tokens, reasoning cost reduction, latency | Unread | Reduces CoT verbosity to 7.6% of tokens while matching CoT accuracy — practical cost/latency reduction for reasoning-heavy vulnerability analysis in Path B. | https://arxiv.org/abs/2502.18600 | Write your notes here…
76 | Which Examples to Annotate for In-Context Learning? Towards Effective and Efficient Selection | Mavromatis et al. | 2023 | arXiv:2310.20046 | Prompt Engineering | few-shot selection, in-context learning, budget constraint, uncertainty sampling, diversity, AdaICL | Unread | AdaICL selects maximally informative few-shot examples under token budget constraints — applicable to selecting the best security examples per scan without exceeding token limits. | https://arxiv.org/abs/2310.20046 | Write your notes here…
77 | DecoPrompt: Decoding Prompts Reduces Hallucinations when Large Language Models Meet False Premises | Xu and Ma | 2024 | arXiv:2411.07457 | Prompt Engineering | hallucination reduction, false premises, decoding prompts, inference-time, no retraining | Unread | Inference-time hallucination reduction by decoding the prompt itself — cost-effective false positive reduction for ZeroTrust.sh without model retraining. | https://arxiv.org/abs/2411.07457 | Write your notes here…
78 | Unlocking Efficiency in Large Language Model Inference: A Comprehensive Survey of Speculative Decoding | Multiple authors | 2024 | arXiv:2401.07851 | Inference Speed | speculative decoding, draft model, parallel verification, inference acceleration, survey | Unread | Comprehensive survey of speculative decoding (small draft model + large verifier) for LLM inference acceleration — core technique for optimizing local Ollama/llama.cpp execution speed. | https://arxiv.org/abs/2401.07851 | Write your notes here…
79 | Keep the Cost Down: A Review on Methods to Optimize LLM's KV-Cache Consumption | Multiple authors | 2024 | arXiv:2407.18003 | Inference Speed | KV-cache, PagedAttention, vLLM, token pruning, VRAM, memory optimization, survey | Unread | Survey of KV-cache optimization strategies (PagedAttention, distributed KV-cache, token pruning) — reduces VRAM footprint for quantized GGUF models in ZeroTrust.sh local inference. | https://arxiv.org/abs/2407.18003 | Write your notes here…
80 | FlashAttention: Fast and Memory-Efficient Exact Attention with IO-Awareness | Dao et al. | 2022 | arXiv:2205.14135 | Inference Speed | flash attention, IO-aware, O(N) memory, foundational, attention efficiency, transformer | Unread | Foundational IO-aware attention reducing memory from O(N²) to O(N) — enables processing longer code snippets with lower memory overhead during semantic analysis. | https://arxiv.org/abs/2205.14135 | Write your notes here…
81 | Why Low-Precision Transformer Training Fails: An Analysis on Flash Attention | Multiple authors | 2025 | arXiv:2510.04212 | Inference Speed | low-precision, GGUF, flash attention, quantization, performance analysis, precision limits | Unread | Analyzes Flash Attention behavior under low-precision quantization — critical for understanding performance characteristics of quantized models used in ZeroTrust.sh's local deployment. | https://arxiv.org/abs/2510.04212 | Write your notes here…
82 | Optimizing LLM Inference Throughput via Memory-aware and SLA-constrained Dynamic Batching | Multiple authors | 2025 | arXiv:2503.05248 | Inference Speed | dynamic batching, throughput, SLA, memory-aware, continuous batching, parallel scanning | Unread | Memory-aware dynamic batching with SLA constraints — optimizes continuous batching for ZeroTrust.sh's parallel Path A/B analysis phases to maximize throughput. | https://arxiv.org/abs/2503.05248 | Write your notes here…
83 | XGrammar: Flexible and Efficient Structured Generation Engine for Large Language Models | Multiple authors | 2024 | arXiv:2411.15100 | Structured Generation | grammar-constrained decoding, BNF, CFG, JSON, zero overhead, structured output, XGrammar | Unread | Grammar-constrained decoding supporting BNF/CFG with zero overhead — enables Path B LLM to output structured JSON vulnerability findings without post-processing verification tokens. | https://arxiv.org/abs/2411.15100 | Write your notes here…
84 | JSONSchemaBench: A Rigorous Benchmark of Structured Outputs for Language Models | Multiple authors | 2025 | arXiv:2501.10868 | Structured Generation | JSON schema, structured output, Guidance, Outlines, XGrammar, benchmark, compliance | Unread | Benchmarks constrained-decoding frameworks (Guidance, Outlines, XGrammar) on JSON Schema compliance — validates structured generation reliability for ZeroTrust.sh vulnerability report output. | https://arxiv.org/abs/2501.10868 | Write your notes here…
85 | SynCode: LLM Generation with Grammar Augmentation | Multiple authors | 2024 | arXiv:2403.01632 | Structured Generation | grammar augmentation, syntactic constraints, output schema, structured generation, alternative to XGrammar | Unread | Grammar-augmented generation enforcing output structure via syntactic constraints — alternative to XGrammar for ensuring ZeroTrust.sh semantic output conforms to fixed schema. | https://arxiv.org/abs/2403.01632 | Write your notes here…
86 | Beyond RAG vs. Long-Context: Learning Distraction-Aware Retrieval for Efficient Knowledge Grounding | Multiple authors | 2024 | arXiv:2509.21865 | Context Management | RAG, long context, distraction-aware, lost in the middle, retrieval, code snippet selection | Unread | Distraction-aware retrieval mitigating 'lost in the middle' effect — addresses how ZeroTrust.sh should select and contextualize code snippets rather than passing entire files to the LLM. | https://arxiv.org/abs/2509.21865 | Write your notes here…
64 | Automated Vulnerability Validation and Verification: A Large Language Model Approach | Lotfi et al. | 2025 | arXiv:2509.24037 | Exploit Automation | CVE exploitation, Docker, automated validation, 70% reproduction rate, offline LLM, PoE layer | Unread | End-to-end LLM pipeline for automated CVE exploitation with Docker orchestration; 70% CVE reproduction rate — directly applicable to ZeroTrust.sh's Approach 3 PoE layer design. | https://arxiv.org/abs/2509.24037 | Write your notes here…
65 | Patch-to-PoC: A Systematic Study of Agentic LLM Systems for Linux Kernel N-Day Reproduction | Pu et al. | 2026 | arXiv:2602.07287 | Exploit Automation | PoC generation, kernel exploit, KernelCTF, VM sandbox, 50%+ success, K-REPRO agent | Unread | Autonomous LLM-based PoC generation from kernel patches with 50%+ success on KernelCTF — K-REPRO agent architecture with VM management informs sandbox PoE design. | https://arxiv.org/abs/2602.07287 | Write your notes here…
66 | PentestAgent: Incorporating LLM Agents to Automated Penetration Testing | Feng et al. | 2024 | arXiv:2411.05185 | Exploit Automation | penetration testing, multi-agent, VulHub, Docker, reconnaissance, exploitation, red team | Unread | Multi-agent framework for autonomous pentest using Docker VulHub environments — demonstrates agent architecture for reconnaissance and exploitation applicable to ZeroTrust.sh red-team layer. | https://arxiv.org/abs/2411.05185 | Write your notes here…
67 | Directed Greybox Fuzzing via Large Language Model | Xu et al. | 2025 | arXiv:2505.03425 | Exploit Automation | LLM fuzzing, path constraint, code generation, 9 new CVEs, 17/20 trigger rate, HGFuzzer | Unread | HGFuzzer uses LLMs to transform path constraints into code generation tasks; discovered 9 new CVEs with 17/20 trigger rate — alternative exploit discovery layer for Approach 3. | https://arxiv.org/abs/2505.03425 | Write your notes here…
68 | PoCGen: Generating Proof-of-Concept Exploits for Vulnerabilities in NPM Packages | Shen et al. | 2025 | arXiv:2506.04962 | Exploit Automation | PoC generation, npm, JavaScript, Node.js, 77% success rate, CVE disclosure, ecosystem-specific | Unread | Autonomous LLM-based PoC for npm vulnerabilities (77% on SecBench.js); 6 PoCs in official CVE disclosures — demonstrates ecosystem-specific PoE applicability for JavaScript targets. | https://arxiv.org/abs/2506.04962 | Write your notes here…
Read Status: Unread (gray) — not yet read · Reading (amber) — in progress · Read (blue) — finished · Reviewed (green) — literature review written