## Execution Overview
ZeroTrust.sh · Approach 1 (Semgrep PoC) · Executive Timeline
Intern: Ton Minh Hoang · VNG ZingPlay Studio · Deadline: 2026-06-20
Date | Milestone | Tasks | Status | Notes
2026-06-09 | M-1 Research & Setup | Install Semgrep CLI · Read YAML rule docs · Write one toy rule end-to-end · Scaffold repo (rules/ tests/ scripts/) | Complete
2026-06-10 | M-2 Python Custom Rules (Day 1 of 2) | Write custom rules: LLM prompt injection (OpenAI / Anthropic / LangChain) · AI bypass comment detection · Set up bad.py / ok.py test pairs | In Progress
2026-06-11 | M-2 Python Custom Rules (Day 2 of 2) | Write custom rule: hardcoded AI service API keys (sk- / sk-ant- / hf_) · Configure community rule packs (p/python, p/owasp-top-ten) · Tune false positive rate with pattern-not
2026-06-12 | M-3 Java Custom Rules (Day 1 of 2) | Validate Java AST shapes with semgrep --dump-ast · Write custom rule: AI bypass comments (Java) · Write custom rule: hardcoded AI service credentials in Java
2026-06-13 | M-3 Java Custom Rules (Day 2 of 2) | Configure community rule packs (p/java, p/java-security-audit) · Tune rules against bad.java / ok.java test pairs · Document precision-recall tradeoff per rule
2026-06-16 | M-4 Test Codebase | AI-generate fake Spring Boot REST API (10–15 files, 800–1 200 LOC) · Embed ≥8 intentional vulnerabilities · Run full rule set · Document detection rate and false positive count
2026-06-17 | M-5 Demo Preparation | Write demo/run_demo.sh with pinned Semgrep version · Full dry-run in fresh terminal · Record 3-minute fallback video
2026-06-18 | M-6 Presentation Narrative | Write pros / cons of Semgrep-only approach · Draft next-step argument for Approach 2 (LLM Verifier + Path B) · Add speaker notes
2026-06-19 | M-7 Jupyter Notebook (Bonus) | Precision and recall per rule · Scan speed (lines/second) · AI-specific detection rate · False positive rate on clean codebase · Charts
2026-06-20 | Presentation | Live CLI demo + narrative delivery to tech lead · Collect approval or actionable feedback
Status key: Complete = delivered · In Progress = active · (blank) = not started · Bonus milestone is time-permitting only

## Research Papers
ZeroTrust.sh · Research Paper Manager
Smart Paper Manager · Use column dropdowns (▾) to filter by Category, Tags, Read Status · Click any column header to sort · Write your notes in column K
# | Title | Authors | Year | Venue | Category | Tags | Read Status | Relevance to ZeroTrust.sh | URL | Literature Review Notes
1 | Automated Vulnerability Detection in Source Code Using Deep Representation Learning | Feng et al. | 2026 | arXiv | ML/DL Detection | CNN, deep representation learning, source code, vulnerability classifier | Unread | CNN-based deep representation learning for vulnerability detection — validates ML classifier gate in Path B Tier 2 | https://arxiv.org/abs/2602.23121 | Write your notes here…
2 | DiverseVul: A New Vulnerable Source Code Dataset for Deep Learning Based Vulnerability Detection | Jia et al. | 2023 | RAID 2023 / ACM | ML/DL Detection | dataset, C/C++, CWE, BigVul alternative, training data, benchmark, 18945 functions | Unread | Largest diverse C/C++ vulnerability dataset (18,945 functions, 150 CWEs) — training data source for Code Vulnerability Classifier | https://arxiv.org/abs/2304.00409 | Write your notes here…
3 | Vulnerability Detection in C/C++ Code with Deep Learning | Multiple authors | 2024 | arXiv | ML/DL Detection | neural network, program slicing, C/C++, deep learning | Unread | Neural networks with program slices for vulnerability detection — informs Tier 2 classifier design | https://arxiv.org/abs/2405.12384 | Write your notes here…
4 | Deep Learning Aided Software Vulnerability Detection: A Survey | Survey authors | 2025 | arXiv | ML/DL Detection | survey, deep learning, vulnerability detection, baseline comparison | Unread | Comprehensive DL survey for vulnerability detection — baseline reference for Tier 2 classifier selection | https://arxiv.org/abs/2503.04002 | Write your notes here…
5 | Software Vulnerability Detection Using a Lightweight Graph Neural Network (VulGNN) | Zhu et al. | 2026 | arXiv | Graph Neural Networks | GNN, lightweight, LLM-parity, local inference, classifier, small model | Unread | Lightweight GNN achieving LLM-parity at 100x smaller size — validates cheap local classifier concept in new architecture | https://arxiv.org/abs/2603.29216 | Write your notes here…
6 | Vul-LMGNNs: Fusing Language Models and Graph Neural Networks for Code Vulnerability Detection | Rong et al. | 2024 | arXiv | Graph Neural Networks | GNN, language model, hybrid, code representation, code LM | Unread | Hybrid code LM + GNN — informs Call Graph + Classifier integration in Path B Tier 2 | https://arxiv.org/abs/2404.14719 | Write your notes here…
7 | Structure-Aware Code Vulnerability Analysis With Graph Neural Networks | Allamanis et al. | 2024 | arXiv | Graph Neural Networks | GNN, Java, structure-aware, vulnerability fixing, commit-level | Unread | GNN-based vulnerability analysis using Java vulnerability-fixing commits — informs structure-aware detection | https://arxiv.org/abs/2307.11454 | Write your notes here…
8 | Graph Neural Networks for Vulnerability Detection: A Counterfactual Explanation | Li et al. | 2024 | arXiv | Graph Neural Networks | GNN, explainability, counterfactual, confidence scoring, interpretability | Unread | Explainability analysis of GNN detection — informs confidence scoring in Dedup layer | https://arxiv.org/abs/2404.15687 | Write your notes here…
9 | ReGVD: Revisiting Graph Neural Networks for Vulnerability Detection | Nguyen et al. | 2022 | ACM/IEEE | Graph Neural Networks | GNN, token sequence, baseline, benchmark, foundational | Unread | Foundational GNN model treating source code as flat token sequences — baseline for Tier 2 classifier | https://dl.acm.org/doi/abs/10.1145/3510454.3516865 | Write your notes here…
10 | LineVD: Statement-level Vulnerability Detection using Graph Neural Networks | Chen et al. | 2022 | arXiv | Graph Neural Networks | GNN, statement-level, line localization, fine-grained, HTML report | Unread | Fine-grained GNN vulnerability localization — informs line-level finding output in HTML report | https://arxiv.org/abs/2203.05181 | Write your notes here…
11 | LLMs in Code Vulnerability Analysis: A Proof of Concept | Kochling et al. | 2026 | arXiv | LLM Code Analysis | LLM, empirical, proof-of-concept, zero-shot, Path B validation | Unread | Empirical PoC for LLM vulnerability analysis — validates LLM Semantic Scan role in Path B Tier 3 | https://arxiv.org/abs/2601.08691 | Write your notes here…
12 | IRIS: LLM-Assisted Static Analysis for Detecting Security Vulnerabilities | Scanlon et al. | 2024 | arXiv | LLM Code Analysis | hybrid SAST+LLM, false positive, 80% FP reduction, IRIS, key paper | Unread | Hybrid SAST+LLM detecting 55/120 vulns + 6 new, reducing FP by 80% — directly validates ZeroTrust.sh hybrid design | https://arxiv.org/abs/2405.17238 | Write your notes here…
13 | Large Language Model for Vulnerability Detection and Repair: Literature Review and the Road Ahead | Zhang et al. | 2025 | ACM TOSEM | LLM Code Analysis | survey, LLM, vulnerability repair, patch generation, comprehensive review | Unread | Comprehensive LLM vulnerability + repair survey — informs patch generation design across all approaches | https://dl.acm.org/doi/10.1145/3708522 | Write your notes here…
14 | Understanding the Effectiveness of LLMs in Detecting Security Vulnerabilities | Steenhoek et al. | 2023 | arXiv | LLM Code Analysis | LLM, prompting strategy, systematic evaluation, false positive, prompt design | Unread | Systematic LLM evaluation with prompting strategy analysis — informs LLM Verifier prompt design in Path A | https://arxiv.org/abs/2311.16169 | Write your notes here…
15 | Large Language Models for Source Code Analysis: Applications, Models and Datasets | Sharma et al. | 2025 | arXiv | LLM Code Analysis | survey, LLM architectures, code analysis, model selection, datasets | Unread | Survey of LLM architectures for code analysis — model selection reference for LLM components | https://arxiv.org/abs/2503.17502 | Write your notes here…
16 | Can Large Language Models Find And Fix Vulnerable Software? | Pearce et al. | 2023 | arXiv | LLM Code Analysis | LLM, detection, repair, empirical evaluation, fix generation | Unread | Empirical evaluation of LLM detection + repair — validates dual-role LLM use in Approaches 2 and 3 | https://arxiv.org/abs/2308.10345 | Write your notes here…
17 | LLM-Driven SAST-Genius: A Hybrid Static Analysis Framework for Comprehensive and Actionable Security | Multiple authors | 2024 | arXiv | Hybrid SAST+LLM | hybrid, SAST+LLM, false positive, 91% FP reduction, Semgrep, key paper | Unread | Hybrid SAST+LLM reducing FP by 91% (225→20 alerts) vs Semgrep alone — strongest validation of ZeroTrust.sh architecture | https://arxiv.org/abs/2509.15433 | Write your notes here…
18 | ZeroFalse: Improving Precision in Static Analysis with LLMs | Scanlon et al. | 2024 | arXiv | Hybrid SAST+LLM | LLM, false positive reduction, static analysis, precision, ZeroFalse | Unread | LLM false positive reduction in static analysis — validates LLM Verifier design in Path A | https://arxiv.org/abs/2510.02534 | Write your notes here…
19 | Combining Large Language Models with Static Analyzers for Code Review Generation | Jaoua et al. | 2025 | arXiv | Hybrid SAST+LLM | LLM, static analysis, code review, patch suggestion, output format | Unread | LLM + static analysis for code review — informs patch suggestion output format | https://arxiv.org/abs/2502.06633 | Write your notes here…
20 | A Contemporary Survey of LLM-Assisted Program Analysis | Survey authors | 2025 | arXiv | Hybrid SAST+LLM | survey, program analysis, LLM, comprehensive, all approaches reference | Unread | Comprehensive survey of LLM program analysis techniques — architecture reference for all three approaches | https://arxiv.org/abs/2502.18474 | Write your notes here…
21 | RepoAudit: An Autonomous LLM-Agent for Repository-Level Code Auditing | Li et al. | 2025 | arXiv | Hybrid SAST+LLM | LLM agent, repository-level, multi-agent, orchestration, Approach 3 | Unread | LLM-agent for repo-level auditing — informs Approach 3 multi-agent orchestration design | https://arxiv.org/abs/2501.18160 | Write your notes here…
22 | Security Vulnerabilities in AI-Generated Code: A Large-Scale Analysis of Public GitHub Repositories | Zhao et al. | 2024 | IEEE/ACM | AI-Generated Code Security | AI-generated code, CWE, GitHub, empirical, 4241 instances, market validation | Unread | 4,241 CWE instances across AI-generated code from 4 tools — empirical validation of the core ZeroTrust.sh problem statement | https://arxiv.org/abs/2510.26103 | Write your notes here…
23 | Prompt Injection Attacks on Agentic Coding Assistants: A Systematic Analysis | Yang et al. | 2026 | arXiv | AI Agent Security | prompt injection, agentic, coding assistant, attack, 85% success rate | Unread | 85%+ attack success rates for prompt injection in agentic assistants — validates ZeroTrust.sh AI-specific threat detection | https://arxiv.org/abs/2601.17548 | Write your notes here…
24 | Security Degradation in Iterative AI Code Generation: A Systematic Analysis of the Paradox | Multiple authors | 2025 | IEEE-ISTAS | AI-Generated Code Security | iterative generation, vibe-coding, security degradation, LLM, threat model | Unread | Iterative LLM interactions without human review introduce new vulnerabilities — validates vibe-coding threat model | https://arxiv.org/abs/2506.11022 | Write your notes here…
25 | Assessing the Quality and Security of AI-Generated Code: A Quantitative Analysis | Multiple authors | 2024 | arXiv | AI-Generated Code Security | AI-generated code, quantitative, security assessment, quality metrics | Unread | Quantitative security analysis of AI-generated code — market validation and threat taxonomy reference | https://arxiv.org/abs/2508.14727 | Write your notes here…
26 | You Still Have to Study: On the Security of LLM Generated Code | Ferrara et al. | 2024 | arXiv | AI-Generated Code Security | Copilot, CWE, 36-40% vulnerability rate, LLM-generated code, pitch statistic | Unread | 36–40% of Copilot code contains CWE vulnerabilities — key statistic for product positioning and pitch | https://arxiv.org/abs/2408.07106 | Write your notes here…
27 | FrugalGPT: How to Use Large Language Models While Reducing Cost and Improving Performance | Eisingerich et al. | 2023 | arXiv | Token Cost Optimization | cascade routing, cost optimization, 98% savings, LLM pipeline, FrugalGPT | Unread | Cascade routing achieving 98% cost savings — theoretical foundation for Cascading Intelligence architecture | https://arxiv.org/abs/2305.05176 | Write your notes here…
28 | Batch Prompting: Efficient Inference with Large Language Model APIs | Rajkumar et al. | 2023 | arXiv | Token Cost Optimization | batch processing, token cost, 5x reduction, inference efficiency | Unread | Batch processing reducing LLM token costs up to 5x — informs Token Budget Controller batching strategy | https://arxiv.org/abs/2301.08721 | Write your notes here…
29 | Token Sugar: Making Source Code Sweeter for LLMs through Token-Efficient Shorthand | Multiple authors | 2025 | arXiv | Token Cost Optimization | token optimization, code representation, shorthand, context compression | Unread | Token optimization for code representation — informs context chunking in Token Budget Controller | https://arxiv.org/abs/2512.08266 | Write your notes here…
30 | Learning to Focus: Context Extraction for Efficient Code Vulnerability Detection with Language Models | Dittmann et al. | 2025 | arXiv | Token Cost Optimization | context filtering, token budget, vulnerability detection, efficiency, focus extraction | Unread | Context filtering for reducing LLM token consumption in vulnerability detection — directly validates Token Budget Controller | https://arxiv.org/abs/2505.17460 | Write your notes here…
31 | Vulnerability Detection with Interprocedural Context in Multiple Languages: Assessing Effectiveness and Cost | Gharibi et al. | 2024 | arXiv | Call Graph & Taint Analysis | interprocedural, multi-language, call graph, LLM detection, effectiveness | Unread | Interprocedural analysis impact on LLM detection across languages — validates Call Graph + CVE Enrichment in Path B | https://arxiv.org/abs/2604.08417 | Write your notes here…
32 | Multi-Agent Taint Specification Extraction for Vulnerability Detection | Zhang et al. | 2026 | arXiv | Call Graph & Taint Analysis | taint analysis, multi-agent, CodeQL, LLM, Approach 3 | Unread | Multi-agent LLM + taint analysis — informs Approach 3 multi-agent architecture with CodeQL/Joern integration | https://arxiv.org/abs/2601.10865 | Write your notes here…
33 | LLMxCPG: Context-Aware Vulnerability Detection Through Code Property Graph-Guided LLMs | Pan et al. | 2024 | arXiv | Call Graph & Taint Analysis | CPG, code property graph, context-aware, LLM, Path B integration | Unread | CPG-guided LLM for context-aware detection — informs CPG integration in Path B call graph analysis | https://arxiv.org/abs/2507.16585 | Write your notes here…
34 | Bridging Code Property Graphs and Language Models for Program Analysis | Mahfouz et al. | 2026 | arXiv | Call Graph & Taint Analysis | CPG, LLM, program analysis, hybrid CPG+LLM, framework | Unread | Framework bridging CPG and LLMs — validates hybrid CPG+LLM design in Path B | https://arxiv.org/abs/2603.24837 | Write your notes here…
35 | Enhancing Software Vulnerability Detection Using Code Property Graphs and Convolutional Neural Networks | Multiple authors | 2025 | arXiv | Call Graph & Taint Analysis | CPG, CNN, local structure, global structure, code classifier training | Unread | CPG+CNN for local and global code structure — informs Code Classifier training in new architecture | https://arxiv.org/abs/2503.18175 | Write your notes here…
36 | VulTrLM: LLM-Assisted Vulnerability Detection via AST Decomposition and Comment Enhancement | Liu et al. | 2025 | Empirical Software Engineering | Call Graph & Taint Analysis | LLM, AST decomposition, semantic enhancement, comment, AST preprocessing | Unread | LLM-assisted AST decomposition for semantic enhancement — informs AST preprocessing in Path B Tier 1 | https://dl.acm.org/doi/10.1007/s10664-025-10738-7 | Write your notes here…
37 | Dataflow Analysis-Inspired Deep Learning for Efficient Vulnerability Detection | Cheng et al. | 2022 | arXiv | Call Graph & Taint Analysis | dataflow analysis, deep learning, CodeQL integration, Path A validation | Unread | Dataflow analysis-inspired DL approach — validates dataflow integration in Path A CodeQL/Joern | https://arxiv.org/abs/2212.08108 | Write your notes here…
38 | Reducing False Positives in Static Bug Detection with LLMs: An Empirical Study in Industry | Dittmann et al. | 2026 | arXiv | Hybrid SAST+LLM | false positive, LLM, industrial study, production scale, empirical | Unread | Industrial study on LLM false positive reduction — validates LLM Verifier design in Path A at production scale | https://arxiv.org/abs/2601.18844 | Write your notes here…
39 | LSAST: Enhancing Cybersecurity through LLM-supported Static Application Security Testing | Multiple authors | 2024 | arXiv | Local LLM Deployment | local LLM, privacy-first, offline, SAST, no cloud API, on-device | Unread | Locally-hostable LLM for SAST without cloud APIs — validates privacy-first local LLM deployment approach | https://arxiv.org/abs/2409.15735 | Write your notes here…
40 | Software Vulnerability Analysis Across Programming Language and Program Representation Landscapes: A Survey | Multiple authors | 2025 | arXiv | Call Graph & Taint Analysis | survey, AST, CFG, PDG, CPG, program representation, multi-language | Unread | Survey of AST, CFG, PDG, CPG representations — reference for program representation selection across all approaches | https://arxiv.org/abs/2503.20244 | Write your notes here…
41 | We Have a Package for You! A Comprehensive Analysis of Package Hallucinations by Code Generating LLMs | Spracklen et al. | 2024 | USENIX Security 2025 | AI Agent Security | slopsquatting, package hallucination, supply chain, npm, pip, 205474 hallucinations, foundational | Unread | Foundational study: 205,474 hallucinated package names across 16 LLMs — commercial at 5.2%, open-source at 21.7%. Baseline threat ZeroTrust.sh must detect. | https://arxiv.org/abs/2406.10279 | Write your notes here…
42 | Importing Phantoms: Measuring LLM Package Hallucination Vulnerabilities | Krishna et al. | 2025 | arXiv:2501.19012 | AI Agent Security | slopsquatting, package hallucination, language comparison, model size, Pareto frontier | Unread | Hallucination rates across languages, model sizes, and task specificity — identifies highest-risk agent configurations for slopsquatting detection. | https://arxiv.org/abs/2501.19012 | Write your notes here…
43 | The Range Shrinks, the Threat Remains: Re-evaluating LLM Package Hallucinations on the 2026 Frontier-Model Cohort | Multiple authors | 2026 | arXiv:2605.17062 | AI Agent Security | slopsquatting, frontier models, Claude, GPT-5, 127 common hallucinations, 2026 benchmark | Unread | Frontier models (Claude Haiku 4.5 at 4.62%, GPT-5.4-mini at 6.10%) still hallucinate; 127 package names all models invent — rich target set for detection rules. | https://arxiv.org/abs/2605.17062 | Write your notes here…
44 | PackMonitor: Enabling Zero Package Hallucinations Through Decoding-Time Monitoring | Liu et al. | 2026 | arXiv:2602.20717 | AI Agent Security | slopsquatting, decoding-time defense, PyPI, npm, authoritative package list, prevention | Unread | Defense via decoding-time intervention constraining generation to authoritative package lists — informs ZeroTrust.sh's detection and verification strategy. | https://arxiv.org/abs/2602.20717 | Write your notes here…
45 | Secure or Suspect? Investigating Package Hallucinations of Shell Command in Original and Quantized LLMs | Haque et al. | 2025 | arXiv:2512.08213 | AI Agent Security | slopsquatting, quantized models, GGUF, shell command, realistic URL mimicry | Unread | Quantized models have significantly higher hallucination rates; fabricated packages mimic GitHub/golang.org URLs — relevant for sophisticated slopsquatting detection. | https://arxiv.org/abs/2512.08213 | Write your notes here…
46 | 'Your AI, My Shell': Demystifying Prompt Injection Attacks on Agentic AI Coding Editors | Liu et al. | 2025 | arXiv:2509.22040 | AI Agent Security | prompt injection, Cursor, repository poisoning, agentic editor, shell execution hijack | Unread | First empirical analysis of Cursor via repository poisoning — attackers inject malicious instructions into dev resources to hijack shell execution. Direct ZeroTrust.sh threat model. | https://arxiv.org/abs/2509.22040 | Write your notes here…
47 | The Dark Side of LLMs: Agent-based Attacks for Complete Computer Takeover | Lupinacci et al. | 2025 | arXiv:2507.06850 | AI Agent Security | privilege escalation, inter-agent trust, 94.4% vulnerable, agent-to-agent attack, safety bypass | Unread | 94.4% of models vulnerable to direct injection; 83.3% to inter-agent trust exploitation — key data for detecting agent-to-agent attack chains in ZeroTrust.sh. | https://arxiv.org/abs/2507.06850 | Write your notes here…
48 | VIGIL: Defending LLM Agents Against Tool Stream Injection via Verify-Before-Commit | Lin et al. | 2026 | arXiv:2601.05755 | AI Agent Security | tool stream injection, SIREN benchmark, verify-before-commit, runtime poisoning, 959 attack cases | Unread | Defense against tool stream injection; SIREN benchmark (959 attack cases) provides test corpus for ZeroTrust.sh detection validation. | https://arxiv.org/abs/2601.05755 | Write your notes here…
49 | Agentic AI Security: Threats, Defenses, Evaluation, and Open Challenges | Datta et al. | 2025 | arXiv:2510.23883 | AI Agent Security | survey, agentic AI, threat taxonomy, tool use, memory, autonomy, planning | Unread | Comprehensive survey of agentic AI threat taxonomy distinguishing autonomous execution risks from traditional LLM safety — essential scope reference for ZeroTrust.sh. | https://arxiv.org/abs/2510.23883 | Write your notes here…
50 | Are AI-assisted Development Tools Immune to Prompt Injection? | Multiple authors | 2026 | arXiv:2603.21642 | AI Agent Security | MCP, tool poisoning, Claude Code, Cursor, Cline, Continue, Gemini CLI, coding tools benchmark | Unread | First empirical analysis of MCP clients (Claude Code, Cursor, Cline, Continue, Gemini CLI) against tool-poisoning attacks — directly relevant to detecting injection in AI tool contexts. | https://arxiv.org/abs/2603.21642 | Write your notes here…
51 | Taming Various Privilege Escalation in LLM-Based Agent Systems: A Mandatory Access Control Framework | Multiple authors | 2026 | arXiv:2601.11893 | AI Agent Security | privilege escalation, MAC framework, SEAgent, formal model, agent security policy | Unread | Formal model of privilege escalation in LLM agents with SEAgent MAC framework — informs detection rules for trust boundary violations in agentic codebases. | https://arxiv.org/abs/2601.11893 | Write your notes here…
52 | BacAlarm: Mining and Simulating Composite API Traffic to Prevent Broken Access Control Violations | Multiple authors | 2025 | arXiv:2512.19997 | Logic Vuln Detection | broken access control, REST API, OWASP API, LLM agent, RAG, anomaly detection | Unread | Broken access control detection in REST APIs via LLM-based agent traffic simulation and ensemble anomaly detection — core to detecting authorization gaps in Path B. | https://arxiv.org/abs/2512.19997 | Write your notes here…
53 | Rethinking Broken Object Level Authorization Attacks Under Zero Trust Principle | Wu et al. | 2025 | arXiv:2507.02309 | Logic Vuln Detection | BOLA, IDOR, zero trust, resource ID dataflow, authorization interval, 35 new CVEs | Unread | BOLAZ: zero-trust defense for BOLA/IDOR via resource ID data flow analysis; discovered 35 new vulnerabilities — directly validates Path B's IDOR detection design. | https://arxiv.org/abs/2507.02309 | Write your notes here…
54 | VULSOLVER: Vulnerability Detection via LLM-Driven Constraint Solving | Li et al. | 2025 | arXiv:2509.00882 | Logic Vuln Detection | LLM, constraint solving, call-chain analysis, 96.29% accuracy, semantic reasoning | Unread | SAST + LLM semantic reasoning with progressive constraint modeling achieves 96.29% accuracy — applicable to detecting contextually-wrong authorization logic. | https://arxiv.org/abs/2509.00882 | Write your notes here…
55 | SAVANT: Vulnerability Detection in Application Dependencies through Semantic-Guided Reachability Analysis | Multiple authors | 2025 | arXiv:2506.17798 | Logic Vuln Detection | semantic preprocessing, LLM, reachability analysis, library API, 83.8% precision | Unread | Semantic preprocessing + LLM context analysis for vulnerable API patterns; 83.8% precision — relevant to detecting missing authorization checks in library calls. | https://arxiv.org/abs/2506.17798 | Write your notes here…
56 | Argus: Reorchestrating Static Analysis via a Multi-Agent Ensemble for Full-Chain Security Vulnerability Detection | Multiple authors | 2025 | arXiv:2604.06633 | Logic Vuln Detection | multi-agent, SAST, false positive reduction, multi-hop reasoning, zero-day, full-chain | Unread | First multi-agent LLM framework for SAST with multi-hop reasoning — discovers zero-day vulnerabilities spanning multiple functions; applicable to detecting business logic flaws. | https://arxiv.org/abs/2604.06633 | Write your notes here…
57 | Benchmarking LLMs and LLM-based Agents in Practical Vulnerability Detection for Code Repositories | Multiple authors | 2025 | ACL 2025 / arXiv:2503.03586 | Logic Vuln Detection | JitVul benchmark, 879 CVEs, interprocedural, ReAct agents, authorization flaws, ACL | Unread | JitVul benchmark (879 CVEs) requires interprocedural analysis; ReAct agents outperform LLMs on auth flaws — suggests agentic approaches for Path B's multi-function context. | https://arxiv.org/abs/2503.03586 | Write your notes here…
58 | Prompting the Priorities: A First Look at Evaluating LLMs for Vulnerability Triage and Prioritization | Multiple authors | 2025 | arXiv:2510.18508 | Logic Vuln Detection | SSVC, triage, prioritization, 384 real-world CVEs, risk surface selection, LLM evaluation | Unread | LLM evaluation on SSVC triage framework with 384 real-world vulnerabilities — methodology for prioritizing high-risk code surfaces before deep Path B analysis. | https://arxiv.org/abs/2510.18508 | Write your notes here…
59 | I Can't Believe It's Not a Valid Exploit | Multiple authors | 2026 | arXiv:2602.04165 | Logic Vuln Detection | PoC-Gym, exploit generation, static analysis guidance, 21% improvement, validation limits | Unread | PoC-Gym framework shows static analysis guidance improves LLM exploit generation by 21% — informs heuristics for filtering false-positive authorization scenarios in Path B. | https://arxiv.org/abs/2602.04165 | Write your notes here…
60 | Mind the Gap: A Practical Attack on GGUF Quantization | Egashira et al. | 2025 | ICML 2025 / arXiv:2505.23786 | Local LLM Deployment | GGUF, quantization, backdoor injection, Ollama, llama.cpp, supply chain, ICML | Unread | Backdoor injection via GGUF quantization errors — essential threat model for ZeroTrust.sh's local LLM deployment: quantized models can exhibit hidden malicious behaviors. | https://arxiv.org/abs/2505.23786 | Write your notes here…
61 | Widening the Gap: Exploiting LLM Quantization via Outlier Injection | Shi et al. | 2025 | arXiv:2605.15152 | Local LLM Deployment | quantization attack, AWQ, GPTQ, GGUF, outlier injection, adversarial, supply chain | Unread | First quantization-conditioned attack affecting AWQ/GPTQ/GGUF — demonstrates supply-chain risks in locally-deployed quantized models; complements GGUF threat model. | https://arxiv.org/abs/2605.15152 | Write your notes here…
62 | A First Look At Efficient And Secure On-Device LLM Inference Against KV Leakage | Yang et al. | 2024 | arXiv:2409.04040 | Local LLM Deployment | on-device LLM, KV cache leakage, FHE, TEE, privacy, local inference security | Unread | Privacy attacks on on-device LLM inference via KV cache leakage — demonstrates how local inference can leak conversation history; relevant to ZeroTrust.sh's privacy-first design. | https://arxiv.org/abs/2409.04040 | Write your notes here…
63 | A Cost-Benefit Analysis of On-Premise Large Language Model Deployment: Breaking Even with Commercial LLM Services | Pan et al. | 2025 | arXiv:2509.18101 | Local LLM Deployment | on-premise, cost analysis, breakeven, Qwen, Llama, Mistral, cloud vs local, value proposition | Unread | Quantifies breakeven for on-premise LLM vs cloud APIs — supports ZeroTrust.sh's value proposition: local deployment becomes cost-competitive at scale. | https://arxiv.org/abs/2509.18101 | Write your notes here…
69 | LLMLingua: Compressing Prompts for Accelerated Inference of Large Language Models | Jiang et al. | 2023 | arXiv:2310.05736 | Prompt Compression | prompt compression, token pruning, 20x compression, budget control, coarse-to-fine | Unread | Iterative token-level compression with budget control; up to 20x compression with minimal loss — directly applicable to compressing code context before LLM security scans. | https://arxiv.org/abs/2310.05736 | Write your notes here…
70 | LLMLingua-2: Data Distillation for Efficient and Faithful Task-Agnostic Prompt Compression | Jiang et al. | 2024 | arXiv:2403.12968 | Prompt Compression | prompt compression, data distillation, token classification, 3-6x faster, 1.6-2.9x latency | Unread | Compression as token classification via GPT-4 distillation; 3–6x faster than LLMLingua with 2–5x compression ratios — ideal for repeated scans of similar code patterns. | https://arxiv.org/abs/2403.12968 | Write your notes here…
71 | LongLLMLingua: Accelerating and Enhancing LLMs in Long Context Scenarios via Prompt Compression | Jiang et al. | 2023 | arXiv:2310.06839 | Prompt Compression | long context, question-aware compression, document reordering, 94% cost reduction, 4x fewer tokens | Unread | Question-aware compression for long-context scenarios; 94% cost reduction on LooGLE — critical for scanning large codebases and enriching prompts with vulnerability databases. | https://arxiv.org/abs/2310.06839 | Write your notes here…
72 | RECOMP: Improving Retrieval-Augmented LMs with Compression and Selective Augmentation | Xu et al. | 2023 | arXiv:2310.04408 | Prompt Compression | RAG, retrieval augmentation, extractive compression, abstractive compression, 6% compression rate | Unread | Compresses retrieved documents in RAG pipelines via extractive and abstractive methods — relevant when ZeroTrust.sh augments prompts with retrieved CVE or security knowledge. | https://arxiv.org/abs/2310.04408 | Write your notes here…
73 | Pruning the Unsurprising: Efficient LLM Reasoning via First-Token Surprisal | Multiple authors | 2025 | arXiv:2508.05988 | Prompt Compression | CoT compression, first-token surprisal, 23.5% token reduction, 43.5% latency reduction, ASAP | Unread | ASAP framework compresses chain-of-thought by 23.5% tokens and 43.5% latency — optimizes reasoning chains in vulnerability analysis without sacrificing accuracy. | https://arxiv.org/abs/2508.05988 | Write your notes here…
74 | Large Language Models as Optimizers (OPRO) | Yang et al. | 2023 | arXiv:2309.03409 | Prompt Engineering | automatic prompt optimization, OPRO, LLM-based refinement, in-context learning, 50% improvement | Unread | Automatic prompt optimization via LLM-based iterative refinement; best prompts beat human-designed by up to 50% — applicable to auto-tuning ZeroTrust.sh security scanning prompts. | https://arxiv.org/abs/2309.03409 | Write your notes here…
75 | Chain of Draft: Thinking Faster by Writing Less | Xu et al. | 2025 | arXiv:2502.18600 | Prompt Engineering | chain of draft, CoT efficiency, 7.6% tokens, reasoning cost reduction, latency | Unread | Reduces CoT verbosity to 7.6% of tokens while matching CoT accuracy — practical cost/latency reduction for reasoning-heavy vulnerability analysis in Path B. | https://arxiv.org/abs/2502.18600 | Write your notes here…
76 | Which Examples to Annotate for In-Context Learning? Towards Effective and Efficient Selection | Mavromatis et al. | 2023 | arXiv:2310.20046 | Prompt Engineering | few-shot selection, in-context learning, budget constraint, uncertainty sampling, diversity, AdaICL | Unread | AdaICL selects maximally informative few-shot examples under token budget constraints — applicable to selecting the best security examples per scan without exceeding token limits. | https://arxiv.org/abs/2310.20046 | Write your notes here…
77 | DecoPrompt: Decoding Prompts Reduces Hallucinations when Large Language Models Meet False Premises | Xu and Ma | 2024 | arXiv:2411.07457 | Prompt Engineering | hallucination reduction, false premises, decoding prompts, inference-time, no retraining | Unread | Inference-time hallucination reduction by decoding the prompt itself — cost-effective false positive reduction for ZeroTrust.sh without model retraining. | https://arxiv.org/abs/2411.07457 | Write your notes here…
78 | Unlocking Efficiency in Large Language Model Inference: A Comprehensive Survey of Speculative Decoding | Multiple authors | 2024 | arXiv:2401.07851 | Inference Speed | speculative decoding, draft model, parallel verification, inference acceleration, survey | Unread | Comprehensive survey of speculative decoding (small draft model + large verifier) for LLM inference acceleration — core technique for optimizing local Ollama/llama.cpp execution speed. | https://arxiv.org/abs/2401.07851 | Write your notes here…
79 | Keep the Cost Down: A Review on Methods to Optimize LLM's KV-Cache Consumption | Multiple authors | 2024 | arXiv:2407.18003 | Inference Speed | KV-cache, PagedAttention, vLLM, token pruning, VRAM, memory optimization, survey | Unread | Survey of KV-cache optimization strategies (PagedAttention, distributed KV-cache, token pruning) — reduces VRAM footprint for quantized GGUF models in ZeroTrust.sh local inference. | https://arxiv.org/abs/2407.18003 | Write your notes here…
80 | FlashAttention: Fast and Memory-Efficient Exact Attention with IO-Awareness | Dao et al. | 2022 | arXiv:2205.14135 | Inference Speed | flash attention, IO-aware, O(N) memory, foundational, attention efficiency, transformer | Unread | Foundational IO-aware attention reducing memory from O(N²) to O(N) — enables processing longer code snippets with lower memory overhead during semantic analysis. | https://arxiv.org/abs/2205.14135 | Write your notes here…
81 | Why Low-Precision Transformer Training Fails: An Analysis on Flash Attention | Multiple authors | 2025 | arXiv:2510.04212 | Inference Speed | low-precision, GGUF, flash attention, quantization, performance analysis, precision limits | Unread | Analyzes Flash Attention behavior under low-precision quantization — critical for understanding performance characteristics of quantized models used in ZeroTrust.sh's local deployment. | https://arxiv.org/abs/2510.04212 | Write your notes here…
82 | Optimizing LLM Inference Throughput via Memory-aware and SLA-constrained Dynamic Batching | Multiple authors | 2025 | arXiv:2503.05248 | Inference Speed | dynamic batching, throughput, SLA, memory-aware, continuous batching, parallel scanning | Unread | Memory-aware dynamic batching with SLA constraints — optimizes continuous batching for ZeroTrust.sh's parallel Path A/B analysis phases to maximize throughput. | https://arxiv.org/abs/2503.05248 | Write your notes here…
83 | XGrammar: Flexible and Efficient Structured Generation Engine for Large Language Models | Multiple authors | 2024 | arXiv:2411.15100 | Structured Generation | grammar-constrained decoding, BNF, CFG, JSON, zero overhead, structured output, XGrammar | Unread | Grammar-constrained decoding supporting BNF/CFG with zero overhead — enables Path B LLM to output structured JSON vulnerability findings without post-processing verification tokens. | https://arxiv.org/abs/2411.15100 | Write your notes here…
84 | JSONSchemaBench: A Rigorous Benchmark of Structured Outputs for Language Models | Multiple authors | 2025 | arXiv:2501.10868 | Structured Generation | JSON schema, structured output, Guidance, Outlines, XGrammar, benchmark, compliance | Unread | Benchmarks constrained-decoding frameworks (Guidance, Outlines, XGrammar) on JSON Schema compliance — validates structured generation reliability for ZeroTrust.sh vulnerability report output. | https://arxiv.org/abs/2501.10868 | Write your notes here…
85 | SynCode: LLM Generation with Grammar Augmentation | Multiple authors | 2024 | arXiv:2403.01632 | Structured Generation | grammar augmentation, syntactic constraints, output schema, structured generation, alternative to XGrammar | Unread | Grammar-augmented generation enforcing output structure via syntactic constraints — alternative to XGrammar for ensuring ZeroTrust.sh semantic output conforms to fixed schema. | https://arxiv.org/abs/2403.01632 | Write your notes here…
86 | Beyond RAG vs. Long-Context: Learning Distraction-Aware Retrieval for Efficient Knowledge Grounding | Multiple authors | 2024 | arXiv:2509.21865 | Context Management | RAG, long context, distraction-aware, lost in the middle, retrieval, code snippet selection | Unread | Distraction-aware retrieval mitigating 'lost in the middle' effect — addresses how ZeroTrust.sh should select and contextualize code snippets rather than passing entire files to the LLM. | https://arxiv.org/abs/2509.21865 | Write your notes here…
64 | Automated Vulnerability Validation and Verification: A Large Language Model Approach | Lotfi et al. | 2025 | arXiv:2509.24037 | Exploit Automation | CVE exploitation, Docker, automated validation, 70% reproduction rate, offline LLM, PoE layer | Unread | End-to-end LLM pipeline for automated CVE exploitation with Docker orchestration; 70% CVE reproduction rate — directly applicable to ZeroTrust.sh's Approach 3 PoE layer design. | https://arxiv.org/abs/2509.24037 | Write your notes here…
65 | Patch-to-PoC: A Systematic Study of Agentic LLM Systems for Linux Kernel N-Day Reproduction | Pu et al. | 2026 | arXiv:2602.07287 | Exploit Automation | PoC generation, kernel exploit, KernelCTF, VM sandbox, 50%+ success, K-REPRO agent | Unread | Autonomous LLM-based PoC generation from kernel patches with 50%+ success on KernelCTF — K-REPRO agent architecture with VM management informs sandbox PoE design. | https://arxiv.org/abs/2602.07287 | Write your notes here…
66 | PentestAgent: Incorporating LLM Agents to Automated Penetration Testing | Feng et al. | 2024 | arXiv:2411.05185 | Exploit Automation | penetration testing, multi-agent, VulHub, Docker, reconnaissance, exploitation, red team | Unread | Multi-agent framework for autonomous pentest using Docker VulHub environments — demonstrates agent architecture for reconnaissance and exploitation applicable to ZeroTrust.sh red-team layer. | https://arxiv.org/abs/2411.05185 | Write your notes here…
67 | Directed Greybox Fuzzing via Large Language Model | Xu et al. | 2025 | arXiv:2505.03425 | Exploit Automation | LLM fuzzing, path constraint, code generation, 9 new CVEs, 17/20 trigger rate, HGFuzzer | Unread | HGFuzzer uses LLMs to transform path constraints into code generation tasks; discovered 9 new CVEs with 17/20 trigger rate — alternative exploit discovery layer for Approach 3. | https://arxiv.org/abs/2505.03425 | Write your notes here…
68 | PoCGen: Generating Proof-of-Concept Exploits for Vulnerabilities in NPM Packages | Shen et al. | 2025 | arXiv:2506.04962 | Exploit Automation | PoC generation, npm, JavaScript, Node.js, 77% success rate, CVE disclosure, ecosystem-specific | Unread | Autonomous LLM-based PoC for npm vulnerabilities (77% on SecBench.js); 6 PoCs in official CVE disclosures — demonstrates ecosystem-specific PoE applicability for JavaScript targets. | https://arxiv.org/abs/2506.04962 | Write your notes here…
Read Status: Unread (gray) — not yet read · Reading (amber) — in progress · Read (blue) — finished · Reviewed (green) — literature review written · Filter tip: click ▾ on Category or Tags header to filter by research area